## Overview
George — Asian Peptide Supplier Qualification
Public-evidence screening converted into a controlled due-diligence programme
Decision date: 20 August 2026 ¦ Not a supplier approval or SAHPRA authorization
DECISION SNAPSHOT
Manufacturers screened |  |  | Conditional Tier A | Tier B manufacturers
10 entities |  |  | RFI priority only | Enhanced diligence required
Laboratories screened |  |  | Open RFI items | No-go risks
4 sites/networks |  |  | Live tracker | Automatic hold criteria
FIRST-WAVE DECISIONS
# | Decision | Required action | Gate
1 | Issue manufacturer RFIs | ScinoPharm, Hybio, Piramal and WuXi, plus one molecule-matched API comparator. | RFI issuance only; no PO or supply award.
2 | Issue laboratory RFIs | Vimta first; SGS Shanghai and Eurofins Kyoto/Kobe in parallel. | Method/site qualification and blind split-sample exercise required.
3 | Keep Intertek bounded | Do not use Mumbai as sole release laboratory on current evidence. | Current verified accreditation scope is non-pharmaceutical.
4 | Commission SA regulatory gap review | Fix applicant, importer, licences, dossier/LoA, testing/release, GDP, PV and recall roles. | No commercial or registration shipment until lawful pathway is confirmed.
5 | Run 90-day qualification | Document review, technical assessment, audits, laboratory exercise, CAPA and board decision. | Re-score using confidential evidence; public scores expire at the decision board.
WORKBOOK CONTENTS
Manufacturer Screen
Laboratory Screen
RFI Tracker
90-Day Plan
Risk & No-Go
Source Register
USE AND CONTROL NOTE
This workbook is a controlled prequalification tool. Tier and score results reflect public evidence only. No supplier, site, product, method, laboratory, batch or transport lane may be approved solely from this file. Final disposition requires regulator-verifiable primary documents, site and method audits, validated testing, quality/technical agreements, a lawful SAHPRA route and formal cross-functional approval.
Note on C10: Source: Final due-diligence report, Executive Summary Decision date: 20 August 2026 Context: KPI label.
Note on F10: Source: Final due-diligence report, Executive Summary Decision date: 20 August 2026 Context: KPI label.
Note on I10: Source: Final due-diligence report, Executive Summary Decision date: 20 August 2026 Context: KPI label.
Note on C12: Source: Final due-diligence report, Executive Summary Decision date: 20 August 2026 Context: KPI interpretation.
Note on F12: Source: Final due-diligence report, Executive Summary Decision date: 20 August 2026 Context: KPI interpretation.
Note on I12: Source: Final due-diligence report, Executive Summary Decision date: 20 August 2026 Context: KPI interpretation.
Note on C14: Source: Final due-diligence report, Executive Summary Decision date: 20 August 2026 Context: KPI label.
Note on F14: Source: Final due-diligence report, Executive Summary Decision date: 20 August 2026 Context: KPI label.
Note on I14: Source: Final due-diligence report, Executive Summary Decision date: 20 August 2026 Context: KPI label.
Note on C16: Source: Final due-diligence report, Executive Summary Decision date: 20 August 2026 Context: KPI interpretation.
Note on F16: Source: Final due-diligence report, Executive Summary Decision date: 20 August 2026 Context: KPI interpretation.
Note on I16: Source: Final due-diligence report, Executive Summary Decision date: 20 August 2026 Context: KPI interpretation.
Note on C22: Source: Final due-diligence report, section 16 Decision date: 20 August 2026 Context: First-wave decision.
Note on D22: Source: Final due-diligence report, section 16 Decision date: 20 August 2026 Context: First-wave decision.
Note on E22: Source: Final due-diligence report, section 16 Decision date: 20 August 2026 Context: First-wave decision.
Note on F22: Source: Final due-diligence report, section 16 Decision date: 20 August 2026 Context: First-wave decision.
Note on C23: Source: Final due-diligence report, section 16 Decision date: 20 August 2026 Context: First-wave decision.
Note on D23: Source: Final due-diligence report, section 16 Decision date: 20 August 2026 Context: First-wave decision.
Note on E23: Source: Final due-diligence report, section 16 Decision date: 20 August 2026 Context: First-wave decision.
Note on F23: Source: Final due-diligence report, section 16 Decision date: 20 August 2026 Context: First-wave decision.
Note on C24: Source: Final due-diligence report, section 16 Decision date: 20 August 2026 Context: First-wave decision.
Note on D24: Source: Final due-diligence report, section 16 Decision date: 20 August 2026 Context: First-wave decision.
Note on E24: Source: Final due-diligence report, section 16 Decision date: 20 August 2026 Context: First-wave decision.
Note on F24: Source: Final due-diligence report, section 16 Decision date: 20 August 2026 Context: First-wave decision.
Note on C25: Source: Final due-diligence report, section 16 Decision date: 20 August 2026 Context: First-wave decision.
Note on D25: Source: Final due-diligence report, section 16 Decision date: 20 August 2026 Context: First-wave decision.
Note on E25: Source: Final due-diligence report, section 16 Decision date: 20 August 2026 Context: First-wave decision.
Note on F25: Source: Final due-diligence report, section 16 Decision date: 20 August 2026 Context: First-wave decision.
Note on C26: Source: Final due-diligence report, section 16 Decision date: 20 August 2026 Context: First-wave decision.
Note on D26: Source: Final due-diligence report, section 16 Decision date: 20 August 2026 Context: First-wave decision.
Note on E26: Source: Final due-diligence report, section 16 Decision date: 20 August 2026 Context: First-wave decision.
Note on F26: Source: Final due-diligence report, section 16 Decision date: 20 August 2026 Context: First-wave decision.
Note on C31: Source: Workbook structure Decision date: 20 August 2026 Context: Internal navigation link.
Note on C32: Source: Workbook structure Decision date: 20 August 2026 Context: Internal navigation link.
Note on C33: Source: Workbook structure Decision date: 20 August 2026 Context: Internal navigation link.
Note on C34: Source: Workbook structure Decision date: 20 August 2026 Context: Internal navigation link.
Note on C35: Source: Workbook structure Decision date: 20 August 2026 Context: Internal navigation link.
Note on C36: Source: Workbook structure Decision date: 20 August 2026 Context: Internal navigation link.
Note on C41: Source: Final due-diligence report, regulatory warning and limitations Decision date: 20 August 2026 Context: Control note.

## Manufacturer Screen
Asian Peptide Manufacturer Screen
Transparent 100-point public-evidence comparison; Tier A is diligence priority, not approval
Blue = hardcoded evidence input ¦ Black = formula ¦ Scores must be replaced after confidential diligence
ID | Manufacturer | Country | Principal Site Chain | Supply Level | Reg 25 | Peptide 20 | Analyt/DI 15 | Market 15 | Resilience 15 | Transparency 10 | Total | Override | Tier | Evidenced Markets | Adverse History / Unknowns | Screening Decision
M01 | WuXi TIDES / WuXi STA (WuXi AppTec) | China | Changzhou and Taixing, Jiangsu (peptide API); Wuxi City, Jiangsu (sterile drug product) | API/DS; separate sterile DP/fill-finish | 19 | 19 | 11 | 12 | 6 | 5 |  | No |  | United States (company-reported 2025 FDA surveillance/PAI); EU, Japan, South Korea, China and Brazil signals require primary-record confirmation; South Africa: Unknown | Incomplete 2023 Wuxi 483 artifact; new Taixing ramp; June 2026 US Section 1260H designation remains under enjoined, pending litigation and is geopolitical, not a GMP finding. | Enhanced RFI and separate API-versus-fill-finish audits; no award.
M02 | Sinopep-Allsino Biopharmaceutical Co., Ltd. | China | Lianyungang, Jiangsu (principal peptide API and claimed finished dose) | API/DS strongest; sterile DP conditional; no device qualification | 16 | 18 | 9 | 10 | 6 | 3 |  | No |  | China; US FDA inspection/DMF evidence; issuer-reported sales to India/Canada and region-level Europe; PMDA list entry; MFDS/ANVISA claims unverified; South Africa: Unknown | CSRC Decision [2025] 148 found materially false financial disclosure and imposed RMB47.4 million company fine; governance/data-reliability red flag, not a GMP finding. | Enhanced RFI focused on API; governance remediation and raw-data audit are gates.
M03 | Hybio Pharmaceutical Co., Ltd. | China | Wuhan (peptide API); Pingshan, Shenzhen (sterile DP/prefilled pen) | API/DS plus evidenced sterile/prefilled DP chain | 21 | 19 | 10 | 14 | 6 | 3 |  | No |  | US (FDA-approved liraglutide ANDA chain); China; EDQM/Europe API signal; Brazil; issuer-reported Chile, Pakistan, Indonesia, Thailand and Vietnam; South Africa: Unknown | 2019 somatostatin assay failure and disclosure delay; Spanish atosiban authorization revoked in 2024; unresolved 2025 customs penalty reference; device chain opaque. | Priority enhanced RFI; audit API and sterile/device chain separately. Tier B because adverse-history closure and current certificates are unresolved.
M04 | CPC Scientific / Medtide (Hangzhou) | China | Qiantang, Hangzhou (commercial peptide API); Rocklin alternate not yet evidenced operational/approved | API/DS only on public evidence | 15 | 18 | 10 | 12 | 5 | 3 |  | No |  | US; China; company-reported Germany/EU, Australia and South Korea; South Africa: Unknown | 2012 FDA registration/listing warning letter; 2024 validation/equipment-qualification observations; 2026 483 contents/classification unavailable. | RFI only; full 2024/2026 FDA packages and remediation effectiveness are hard gates.
M05 | Piramal Pharma Solutions, Turbhe | India | Turbhe, Navi Mumbai (peptide API); Lexington, US is separate sterile DP site | API/DS; Turbhe is not evidenced as sterile DP | 21 | 17 | 9 | 13 | 6 | 4 |  | No |  | US inspection/supply evidence; WHO-prequalified oxytocin and carbetocin API; EDQM-linked oxytocin evidence; South Africa: no Turbhe-specific linkage found | Six FDA observations included quality-unit, repeated deviation, complaint, cleaning, batch-record and temperature-control deficiencies. | Priority RFI for WHO-backed products; require FDA CAPA effectiveness and lane challenge before audit closure.
M06 | Shilpa Pharma Lifesciences / Shilpa Medicare | India | Raichur Units I/II (API); Jadcherla Unit IV (separate finished dose) | API/DS; sterile DP not peptide-qualified and enforcement-affected | 17 | 16 | 8 | 11 | 6 | 4 |  | No |  | EDQM CEP signals for desmopressin/octreotide; US inspection/DMF claim; Japan and Brazil inspection signals; South Africa: Unknown | Raichur Unit I 2025 VAI; Jadcherla finished-dose 2020 FDA warning letter and unresolved public Import Alert 66-40 status. | RFI for a CEP-backed API only; exclude Jadcherla from proposed chain absent verified enforcement closure and peptide-specific qualification.
M07 | PeptiStar Inc. | Japan | Settsu, Osaka single campus (R&D and Manufacturing Buildings 1/2) | Non-sterile API/DS only | 11 | 17 | 10 | 5 | 7 | 6 |  | No |  | No specific regulated therapeutic country/site/product linkage publicly evidenced; South Africa: Unknown | No public enforcement located, but absence is not proof of a clean history; ownership/control and commercial batch history are incomplete. | Confidential RFI and audit candidate only after Japanese licence/GMP and customer-authorized dossier evidence.
M08 | Ajinomoto Bio-Pharma Services (Japan) | Japan | Tokai, Mie (candidate AJIPHASE); Osaka/GeneDesign; Kawasaki is separate API/R&D context | API/DS platform; no current in-group sterile DP | 12 | 18 | 8 | 5 | 7 | 5 |  | No |  | No named therapeutic-peptide market linked to Tokai/Osaka; US AJIPHASE approval disclosure appears oligonucleotide; South Africa: Unknown | Kawasaki 2025 FDA 483/VAI signal for investigations, document control and material compatibility; not automatically attributable to Tokai/Osaka. | Technology-fit RFI only; require precise legal/site flow and independently verified GMP evidence before audit.
M09 | HLB PEP Co., Ltd. | South Korea | Jangseong Plant 1 and Osong Plant 2 (peptide API); Gwangju is non-GMP/pilot | API/DS only | 16 | 15 | 8 | 10 | 6 | 3 |  | No |  | South Korea; active US Type II DMFs; reported Japan recognition and historical India export authorization; South Africa: Unknown | Confirmed 2025 one-month MFDS suspension for missing 2022/2023 APQRs on two Jangseong products; closure/effectiveness package unavailable. | RFI for a defined API only; APQR retrospective impact assessment and MFDS closure are hard gates.
M10 | ScinoPharm Taiwan, Ltd. | Taiwan | Tainan (peptide API, sterile fill-finish, packaging and cold-chain GDP); Changshu, China is separate | API/DS plus TFDA-evidenced sterile DP and packaging | 23 | 18 | 11 | 14 | 7 | 6 |  | No |  | United States (ANDA-linked glatiramer PFS); Taiwan; historical/current signals for Europe, Japan and Brazil; South Africa: Unknown | Historical 2012 VAI reported secondarily and 2015 FDA 483/EIR indexed; current primary FDA classifications/CAPA not reviewed. | Tier A for RFI priority only, conditional on historical FDA package, site genealogy, sterile assurance, supplier map and SAHPRA pathway.
SCORING WEIGHTS AND INTERPRETATION
Criterion | Weight | Interpretation
Regulatory/site evidence | 25 | Exact legal entity, address, current licences/certificates, inspections, product/site scope and closure status.
Peptide capability | 20 | Therapeutic GMP API/DS evidence; synthesis, purification, isolation and scale; sterile/device separately evidenced.
Analytical/data integrity | 15 | Peptide control strategy, validation, reference standards, OOS/OOT/CAPA, audit trails and raw-data governance.
Regulated-market/export | 15 | Named product/dossier/label/CEP/WHO linkage outweighs registration, filing or generic export claims.
Resilience/traceability | 15 | Site/train redundancy, critical-material genealogy, dual sourcing, subcontractor visibility and qualified lanes.
Transparency/adverse response | 10 | Complete records, root cause, CAPA effectiveness, recurrence prevention and consistent claims.
Note on C9: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M01.
Note on D9: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M01.
Note on E9: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M01.
Note on F9: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M01.
Note on G9: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M01.
Note on H9: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M01.
Note on I9: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M01.
Note on J9: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M01.
Note on K9: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M01.
Note on L9: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M01.
Note on M9: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M01.
Note on O9: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Critical public-red-flag override; update after diligence.
Note on Q9: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Evidenced/bounded markets for M01.
Note on R9: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Adverse-history screen for M01.
Note on S9: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence decision for M01.
Note on C10: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M02.
Note on D10: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M02.
Note on E10: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M02.
Note on F10: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M02.
Note on G10: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M02.
Note on H10: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M02.
Note on I10: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M02.
Note on J10: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M02.
Note on K10: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M02.
Note on L10: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M02.
Note on M10: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M02.
Note on O10: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Critical public-red-flag override; update after diligence.
Note on Q10: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Evidenced/bounded markets for M02.
Note on R10: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Adverse-history screen for M02.
Note on S10: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence decision for M02.
Note on C11: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M03.
Note on D11: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M03.
Note on E11: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M03.
Note on F11: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M03.
Note on G11: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M03.
Note on H11: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M03.
Note on I11: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M03.
Note on J11: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M03.
Note on K11: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M03.
Note on L11: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M03.
Note on M11: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M03.
Note on O11: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Critical public-red-flag override; update after diligence.
Note on Q11: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Evidenced/bounded markets for M03.
Note on R11: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Adverse-history screen for M03.
Note on S11: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence decision for M03.
Note on C12: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M04.
Note on D12: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M04.
Note on E12: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M04.
Note on F12: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M04.
Note on G12: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M04.
Note on H12: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M04.
Note on I12: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M04.
Note on J12: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M04.
Note on K12: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M04.
Note on L12: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M04.
Note on M12: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M04.
Note on O12: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Critical public-red-flag override; update after diligence.
Note on Q12: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Evidenced/bounded markets for M04.
Note on R12: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Adverse-history screen for M04.
Note on S12: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence decision for M04.
Note on C13: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M05.
Note on D13: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M05.
Note on E13: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M05.
Note on F13: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M05.
Note on G13: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M05.
Note on H13: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M05.
Note on I13: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M05.
Note on J13: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M05.
Note on K13: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M05.
Note on L13: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M05.
Note on M13: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M05.
Note on O13: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Critical public-red-flag override; update after diligence.
Note on Q13: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Evidenced/bounded markets for M05.
Note on R13: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Adverse-history screen for M05.
Note on S13: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence decision for M05.
Note on C14: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M06.
Note on D14: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M06.
Note on E14: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M06.
Note on F14: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M06.
Note on G14: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M06.
Note on H14: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M06.
Note on I14: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M06.
Note on J14: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M06.
Note on K14: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M06.
Note on L14: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M06.
Note on M14: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M06.
Note on O14: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Critical public-red-flag override; update after diligence.
Note on Q14: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Evidenced/bounded markets for M06.
Note on R14: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Adverse-history screen for M06.
Note on S14: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence decision for M06.
Note on C15: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M07.
Note on D15: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M07.
Note on E15: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M07.
Note on F15: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M07.
Note on G15: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M07.
Note on H15: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M07.
Note on I15: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M07.
Note on J15: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M07.
Note on K15: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M07.
Note on L15: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M07.
Note on M15: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M07.
Note on O15: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Critical public-red-flag override; update after diligence.
Note on Q15: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Evidenced/bounded markets for M07.
Note on R15: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Adverse-history screen for M07.
Note on S15: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence decision for M07.
Note on C16: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M08.
Note on D16: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M08.
Note on E16: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M08.
Note on F16: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M08.
Note on G16: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M08.
Note on H16: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M08.
Note on I16: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M08.
Note on J16: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M08.
Note on K16: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M08.
Note on L16: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M08.
Note on M16: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M08.
Note on O16: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Critical public-red-flag override; update after diligence.
Note on Q16: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Evidenced/bounded markets for M08.
Note on R16: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Adverse-history screen for M08.
Note on S16: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence decision for M08.
Note on C17: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M09.
Note on D17: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M09.
Note on E17: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M09.
Note on F17: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M09.
Note on G17: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M09.
Note on H17: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M09.
Note on I17: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M09.
Note on J17: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M09.
Note on K17: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M09.
Note on L17: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M09.
Note on M17: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M09.
Note on O17: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Critical public-red-flag override; update after diligence.
Note on Q17: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Evidenced/bounded markets for M09.
Note on R17: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Adverse-history screen for M09.
Note on S17: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence decision for M09.
Note on C18: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M10.
Note on D18: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M10.
Note on E18: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M10.
Note on F18: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M10.
Note on G18: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Manufacturer dataset row M10.
Note on H18: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M10.
Note on I18: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M10.
Note on J18: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M10.
Note on K18: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M10.
Note on L18: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M10.
Note on M18: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence score component for M10.
Note on O18: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Critical public-red-flag override; update after diligence.
Note on Q18: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Evidenced/bounded markets for M10.
Note on R18: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Adverse-history screen for M10.
Note on S18: Source: asian_peptide_manufacturers.csv Decision date: 20 August 2026 Context: Public-evidence decision for M10.
Note on C24: Source: Final report section 2 Decision date: 20 August 2026 Context: Scoring model.
Note on D24: Source: Final report section 2 Decision date: 20 August 2026 Context: Scoring model.
Note on E24: Source: Final report section 2 Decision date: 20 August 2026 Context: Scoring model.
Note on C25: Source: Final report section 2 Decision date: 20 August 2026 Context: Scoring model.
Note on D25: Source: Final report section 2 Decision date: 20 August 2026 Context: Scoring model.
Note on E25: Source: Final report section 2 Decision date: 20 August 2026 Context: Scoring model.
Note on C26: Source: Final report section 2 Decision date: 20 August 2026 Context: Scoring model.
Note on D26: Source: Final report section 2 Decision date: 20 August 2026 Context: Scoring model.
Note on E26: Source: Final report section 2 Decision date: 20 August 2026 Context: Scoring model.
Note on C27: Source: Final report section 2 Decision date: 20 August 2026 Context: Scoring model.
Note on D27: Source: Final report section 2 Decision date: 20 August 2026 Context: Scoring model.
Note on E27: Source: Final report section 2 Decision date: 20 August 2026 Context: Scoring model.
Note on C28: Source: Final report section 2 Decision date: 20 August 2026 Context: Scoring model.
Note on D28: Source: Final report section 2 Decision date: 20 August 2026 Context: Scoring model.
Note on E28: Source: Final report section 2 Decision date: 20 August 2026 Context: Scoring model.
Note on C29: Source: Final report section 2 Decision date: 20 August 2026 Context: Scoring model.
Note on D29: Source: Final report section 2 Decision date: 20 August 2026 Context: Scoring model.
Note on E29: Source: Final report section 2 Decision date: 20 August 2026 Context: Scoring model.

## Laboratory Screen
Independent Laboratory Qualification Screen
Each site and method requires primary-scope verification, audit, method qualification and split-sample evidence
No third-party laboratory substitutes for manufacturer GMP, registered specifications or authorized batch release
ID | Laboratory | Country | Site | Score | Tier | Verified Evidence Boundary | Peptide-Relevant Methods | Preliminary Role | Qualification Status | RFI Owner | Audit Status | Split-Sample Result | Final Disposition
L01 | SGS Shanghai Health Science Laboratory | China | Yishan Road, Shanghai | 66 | B | CMA certificate includes site through 2029; claimed ISO/IEC 17025/CNAS scope annex not obtained; company reports 2024 FDA inspection with no 483, but official EIR/classification unavailable. | Strong conditional E&L; potential LC-MS, HPLC/UPLC, residual solvents, elemental impurities, microbiology and sterility. Water, counter-ion, particulates, CCI and excursions not site-verified. | Specialist/conditional RFI; not sole release laboratory. | Not Started |  | Not Started | Not Run | Hold
L02 | Eurofins Analytical Science Laboratories, Kyoto and Kobe | Japan | Kyoto and Kobe, Japan | 64 | B | PMDA 2024 Kyoto compliant result for undisclosed application scope; Kyoto FDA 2024 Form 483 unresolved; no site ISO 17025 scope verified; Kobe authority unknown. | Broad LC-MS sequence/identity, HPLC/UPLC, GC, KF, ICP, microbiology/sterility, particulates, stability, CCI and E&L potential; exact site/method allocation required. | Specialist/conditional; site- and method-specific audit required. | Not Started |  | Not Started | Not Run | Hold
L03 | Vimta Labs Limited, Life Sciences Facility | India | Genome Valley, Hyderabad | 70 | B | Current NABL ISO/IEC 17025 certificate through 2028 but annex absent; current WHO-prequalified QCL listing; exact-site FDA 2023 VAI; veterinary GMP stability scope through 2027. | Strong conditional LC-MS/intact mass, HPLC/UPLC/SEC, elemental, microbiology, sterility, endotoxin, particulates and stability. CCI/excursion not verified. | Priority laboratory RFI; blind split-sample qualification before use. | Not Started |  | Not Started | Not Run | Hold
L04 | Intertek Pharmaceutical Services India, Mumbai | India | Tex Centre, Andheri East, Mumbai | 46 | C | Current IAS ISO 17025 scope is environmental, not pharmaceutical; prior NABL scope expired and was non-pharma; claimed MH-FDA approval lacks primary certificate; no FDA site record verified. | Marketing-supported HPLC, LC-MS/MS, GC, ICP, stability and E&L research potential, but required peptide and microbiology methods lack current site-specific regulated scope. | Do not use as sole release lab; RFI only for bounded specialist research pending primary licences/scopes. | Not Started |  | Not Started | Not Run | Hold
MINIMUM METHOD-QUALIFICATION DOMAINS
Domain | Required evidence
Identity / sequence | LC-MS intact mass and peptide mapping; sequence coverage; orthogonal identity; disulfide/modification confirmation.
Assay / purity | Stability-indicating HPLC/UPLC; related substances; response factors; LOQ; forced degradation and mass balance.
Process residuals | Residual solvents, counter-ion, water, elemental/genotoxic/nitrosamine and resin/linker-derived impurities as applicable.
Micro / sterile | Bioburden, endotoxin, microbial limits, sterility, particulates and method suitability for the exact matrix.
Container / device | CCI, E&L, silicone/tungsten, dose accuracy and component compatibility where relevant.
Stability / excursions | Mapped chambers, alarms, ICH conditions, freeze/thaw, light/heat and temperature-excursion protocol.
Data integrity | Native files, metadata, audit trails, integration history, access roles, backup/restore, OOS/OOT/CAPA and raw-data rights.
Custody / retains | Tamper seals, logger review, receipt checks, LIMS traceability, controlled aliquots, retains and no unapproved subcontracting.
Note on C9: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Laboratory dataset row L01.
Note on D9: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Laboratory dataset row L01.
Note on E9: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Laboratory dataset row L01.
Note on F9: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Laboratory dataset row L01.
Note on G9: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Public-evidence screening score.
Note on H9: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Public-evidence tier.
Note on I9: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Verified evidence boundary.
Note on J9: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Potential peptide methods; site/method verification required.
Note on K9: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Preliminary role.
Note on L9: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable qualification input.
Note on M9: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable qualification input.
Note on N9: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable qualification input.
Note on O9: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable qualification input.
Note on P9: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable qualification input.
Note on C10: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Laboratory dataset row L02.
Note on D10: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Laboratory dataset row L02.
Note on E10: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Laboratory dataset row L02.
Note on F10: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Laboratory dataset row L02.
Note on G10: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Public-evidence screening score.
Note on H10: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Public-evidence tier.
Note on I10: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Verified evidence boundary.
Note on J10: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Potential peptide methods; site/method verification required.
Note on K10: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Preliminary role.
Note on L10: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable qualification input.
Note on M10: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable qualification input.
Note on N10: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable qualification input.
Note on O10: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable qualification input.
Note on P10: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable qualification input.
Note on C11: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Laboratory dataset row L03.
Note on D11: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Laboratory dataset row L03.
Note on E11: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Laboratory dataset row L03.
Note on F11: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Laboratory dataset row L03.
Note on G11: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Public-evidence screening score.
Note on H11: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Public-evidence tier.
Note on I11: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Verified evidence boundary.
Note on J11: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Potential peptide methods; site/method verification required.
Note on K11: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Preliminary role.
Note on L11: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable qualification input.
Note on M11: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable qualification input.
Note on N11: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable qualification input.
Note on O11: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable qualification input.
Note on P11: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable qualification input.
Note on C12: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Laboratory dataset row L04.
Note on D12: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Laboratory dataset row L04.
Note on E12: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Laboratory dataset row L04.
Note on F12: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Laboratory dataset row L04.
Note on G12: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Public-evidence screening score.
Note on H12: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Public-evidence tier.
Note on I12: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Verified evidence boundary.
Note on J12: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Potential peptide methods; site/method verification required.
Note on K12: Source: asian_peptide_laboratories.csv Decision date: 20 August 2026 Context: Preliminary role.
Note on L12: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable qualification input.
Note on M12: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable qualification input.
Note on N12: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable qualification input.
Note on O12: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable qualification input.
Note on P12: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable qualification input.
Note on C18: Source: Final report sections 8, 14 and 15 Decision date: 20 August 2026 Context: Laboratory qualification domain.
Note on D18: Source: Final report sections 8, 14 and 15 Decision date: 20 August 2026 Context: Laboratory qualification domain.
Note on C19: Source: Final report sections 8, 14 and 15 Decision date: 20 August 2026 Context: Laboratory qualification domain.
Note on D19: Source: Final report sections 8, 14 and 15 Decision date: 20 August 2026 Context: Laboratory qualification domain.
Note on C20: Source: Final report sections 8, 14 and 15 Decision date: 20 August 2026 Context: Laboratory qualification domain.
Note on D20: Source: Final report sections 8, 14 and 15 Decision date: 20 August 2026 Context: Laboratory qualification domain.
Note on C21: Source: Final report sections 8, 14 and 15 Decision date: 20 August 2026 Context: Laboratory qualification domain.
Note on D21: Source: Final report sections 8, 14 and 15 Decision date: 20 August 2026 Context: Laboratory qualification domain.
Note on C22: Source: Final report sections 8, 14 and 15 Decision date: 20 August 2026 Context: Laboratory qualification domain.
Note on D22: Source: Final report sections 8, 14 and 15 Decision date: 20 August 2026 Context: Laboratory qualification domain.
Note on C23: Source: Final report sections 8, 14 and 15 Decision date: 20 August 2026 Context: Laboratory qualification domain.
Note on D23: Source: Final report sections 8, 14 and 15 Decision date: 20 August 2026 Context: Laboratory qualification domain.
Note on C24: Source: Final report sections 8, 14 and 15 Decision date: 20 August 2026 Context: Laboratory qualification domain.
Note on D24: Source: Final report sections 8, 14 and 15 Decision date: 20 August 2026 Context: Laboratory qualification domain.
Note on C25: Source: Final report sections 8, 14 and 15 Decision date: 20 August 2026 Context: Laboratory qualification domain.
Note on D25: Source: Final report sections 8, 14 and 15 Decision date: 20 August 2026 Context: Laboratory qualification domain.

## RFI Tracker
Supplier and Laboratory Due-Diligence RFI Tracker
Controlled request list for product-, site-, batch-, method- and lane-specific qualification
Complete each field; use Unknown / Not Applicable explicitly; high-priority share is intentionally limited
Request ID | Workstream | Detailed Request | Priority | Applies To | Target Entity | Gate | Owner | Status | Date Requested | SLA Days | Due Date | Date Received | Review Outcome | Evidence Link | Days Outstanding | Notes
RFI-001 | Corporate & Legal | Provide contracting entity, all manufacturing/testing affiliates, corporate numbers, ownership/UBO and authorized signatories. | High | Manufacturers |  | Pre-audit |  | Not Started |  | 10 |  |  | Pending
RFI-002 | Corporate & Legal | Provide legal title or lease evidence for each proposed site and reconcile every address across licences, FEI, certificates and invoices. | High | Manufacturers & Laboratories |  | Pre-audit |  | Not Started |  | 10 |  |  | Pending
RFI-003 | Corporate & Legal | Provide current organization charts for corporate, site quality, production, QC, regulatory, supply and pharmacovigilance interfaces. | Medium | Manufacturers & Laboratories |  | Pre-audit |  | Not Started |  | 10 |  |  | Pending
RFI-004 | Corporate & Legal | Provide audited financial statements, insurance certificates, business-continuity funding and material litigation/sanctions disclosures. | Medium | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-005 | Corporate & Legal | Declare all brokers, agents, distributors and consultants in the proposed transaction and confirm no therapeutic material is sourced from traders. | High | Manufacturers |  | No-Go |  | Not Started |  | 10 |  |  | Pending
RFI-006 | Corporate & Legal | Provide anti-bribery, sanctions, export-control, modern-slavery and conflict-of-interest declarations. | Medium | Manufacturers & Laboratories |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-007 | Regulatory & Licences | Provide current local manufacturing/testing licences and every annex for the exact legal entity, address, building, activity and dosage form. | High | Manufacturers & Laboratories |  | No-Go |  | Not Started |  | 10 |  |  | Pending
RFI-008 | Regulatory & Licences | Provide current GMP/GDP/GLP/ISO certificates and full scope schedules, with issuing-body verification links and expiry/status. | High | Manufacturers & Laboratories |  | Pre-audit |  | Not Started |  | 10 |  |  | Pending
RFI-009 | Regulatory & Licences | List the last three regulator inspections for each proposed site, including dates, authority, scope, observations, responses, EIR/final classification and commitments. | High | Manufacturers & Laboratories |  | Pre-audit |  | Not Started |  | 10 |  |  | Pending
RFI-010 | Regulatory & Licences | Disclose all warning letters, import alerts, non-compliance statements, recalls, suspensions, licence restrictions and regulator commitments for ten years. | High | Manufacturers & Laboratories |  | No-Go |  | Not Started |  | 10 |  |  | Pending
RFI-011 | Regulatory & Licences | Provide evidence of closure and CAPA effectiveness for every public adverse event identified in the George research report. | High | Manufacturers & Laboratories |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-012 | Regulatory & Licences | Provide product-specific CEP, DMF, ASMF, LoA, approved dossier references and current status; distinguish filing from approval. | High | Manufacturers |  | Pre-audit |  | Not Started |  | 10 |  |  | Pending
RFI-013 | Regulatory & Licences | Provide a country-by-country list of products actually supplied from the proposed site, with approval/label/dossier evidence and no inferred customers. | Medium | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-014 | Regulatory & Licences | Confirm whether the proposed product/site has any SAHPRA history, inspection, dossier linkage, deficiency question or local partner relationship. | High | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-015 | Regulatory & Licences | Provide all regulatory change commitments affecting route, site, raw material, specification, method, container, device, storage or shelf life. | High | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-016 | Product & Site Genealogy | Define the exact peptide, sequence, salt/counter-ion, grade, dosage form, strength, presentation, annual volume and target markets. | High | Manufacturers |  | Pre-audit |  | Not Started |  | 10 |  |  | Pending
RFI-017 | Product & Site Genealogy | Map every physical site, building, room, line and equipment train for synthesis, purification, isolation, milling, testing, release, storage and export. | High | Manufacturers |  | No-Go |  | Not Started |  | 10 |  |  | Pending
RFI-018 | Product & Site Genealogy | Map every sterile formulation, filtration, filling, lyophilization, sterilization, device assembly, packaging and serialization site where applicable. | High | Manufacturers |  | No-Go |  | Not Started |  | 10 |  |  | Pending
RFI-019 | Product & Site Genealogy | Identify the legal batch-release site and responsible quality roles for API, drug product, device and final packaged product. | High | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-020 | Product & Site Genealogy | Describe the research/non-GMP-to-GMP transfer boundary and prove that no research-use material enters therapeutic manufacture. | High | Manufacturers |  | No-Go |  | Not Started |  | 10 |  |  | Pending
RFI-021 | Product & Site Genealogy | Provide the proposed registered supply-chain diagram and reconcile it to contracts, licences, quality agreements and shipping documents. | High | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-022 | Process & Validation | Provide detailed process flow, synthesis route, scale, CPPs, CQAs, in-process controls, hold times and material balance. | High | Manufacturers |  | Pre-audit |  | Not Started |  | 10 |  |  | Pending
RFI-023 | Process & Validation | Provide three PPQ or representative commercial-scale batch records and summary reports for the proposed site/train. | High | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-024 | Process & Validation | Provide CPV/APR/PQR trends for yield, purity, critical impurities, deviations, OOS/OOT, complaints and changes for 36 months. | High | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-025 | Process & Validation | Provide impurity fate/purge and control strategy for deletions, insertions, truncations, epimers, oxidation, deamidation/aspartimide and aggregation. | High | Manufacturers |  | Pre-audit |  | Not Started |  | 10 |  |  | Pending
RFI-026 | Process & Validation | Provide controls for residual protecting groups, scavengers, coupling reagents, counter-ion, solvents, elemental/genotoxic/nitrosamine and resin/linker leachables. | High | Manufacturers |  | Pre-audit |  | Not Started |  | 10 |  |  | Pending
RFI-027 | Process & Validation | Provide cleaning validation, HBEL/carryover rationale, campaign strategy and shared-equipment product matrix. | High | Manufacturers |  | No-Go |  | Not Started |  | 10 |  |  | Pending
RFI-028 | Process & Validation | List all reprocessing, rework, atypical yield and low-purity batches for 36 months with approved rationale and outcome. | Medium | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-029 | Process & Validation | Provide equipment/utility qualification, preventive maintenance, calibration, alarms, backup utilities and disaster recovery for critical trains. | Medium | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-030 | Analytical & Data Integrity | Provide the registered release and stability specification, pharmacopoeial commitments and method list for API and drug product. | High | Manufacturers & Laboratories |  | Pre-audit |  | Not Started |  | 10 |  |  | Pending
RFI-031 | Analytical & Data Integrity | Provide method validation/verification/transfer reports for identity, assay, purity, related substances and all applicable residual/physical/microbial tests. | High | Manufacturers & Laboratories |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-032 | Analytical & Data Integrity | Provide reference-standard qualification, potency/water/counter-ion assignment, traceability, storage, retest and reconciliation controls. | High | Manufacturers & Laboratories |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-033 | Analytical & Data Integrity | Provide representative CoAs and complete native raw-data packages, including chromatograms, spectra, metadata, audit trails and integration history. | High | Manufacturers & Laboratories |  | Pre-audit |  | Not Started |  | 10 |  |  | Pending
RFI-034 | Analytical & Data Integrity | Provide OOS, OOT, deviation, invalidation, retest/resample and CAPA metrics and case lists for 36 months. | High | Manufacturers & Laboratories |  | Pre-audit |  | Not Started |  | 10 |  |  | Pending
RFI-035 | Analytical & Data Integrity | Provide chromatography and laboratory-system user-role matrices, administrator independence, audit-trail review and deleted/aborted sequence controls. | High | Manufacturers & Laboratories |  | No-Go |  | Not Started |  | 10 |  |  | Pending
RFI-036 | Analytical & Data Integrity | Provide computerized-system inventory, validation status, backup/restore tests, cybersecurity controls, data retention and disaster recovery. | Medium | Manufacturers & Laboratories |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-037 | Analytical & Data Integrity | Identify every outsourced test, physical site, method, regulated scope, raw-data owner and quality agreement. | High | Manufacturers & Laboratories |  | No-Go |  | Not Started |  | 10 |  |  | Pending
RFI-038 | Raw Materials & Supply Network | Provide manufacturer, site and country of origin for each protected/non-natural amino acid, resin/linker/anchor, side chain and critical building block. | High | Manufacturers |  | Pre-audit |  | Not Started |  | 10 |  |  | Pending
RFI-039 | Raw Materials & Supply Network | Provide approved supplier list, qualification/audit status, quality agreements, incoming specification and change-notification terms for critical materials. | High | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-040 | Raw Materials & Supply Network | Identify single-source items, second-source qualification status, safety-stock days, lead times and allocation rights. | High | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-041 | Raw Materials & Supply Network | Provide resin/linker leachables, chiral impurity, TSE/BSE, elemental, nitrosamine/genotoxic and solvent-origin risk assessments. | Medium | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-042 | Raw Materials & Supply Network | Provide country/origin and recovery controls for acetonitrile, DMF/NMP/DCM, TFA, scavengers, coupling reagents and chromatography media. | Medium | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-043 | Raw Materials & Supply Network | Map all subcontractors for external testing, sterilization, storage, device/components, packaging, transport and final release. | High | Manufacturers |  | No-Go |  | Not Started |  | 10 |  |  | Pending
RFI-044 | Raw Materials & Supply Network | Provide capacity, utilization, campaign calendar, purification/lyophilizer bottleneck, reserved capacity and surge plan for the forecast demand. | High | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-045 | Raw Materials & Supply Network | Provide alternate train/site status, dossier readiness, transfer package, recovery time objective and recent BCP exercise evidence. | High | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-046 | Sterile, Device & Packaging | Provide contamination-control strategy, facility/flow diagrams, cleanroom grades, isolator/RABS qualification and utility monitoring. | High | Sterile Manufacturers |  | Pre-audit |  | Not Started |  | 10 |  |  | Pending
RFI-047 | Sterile, Device & Packaging | Provide APS/media-fill matrix and reports, including interventions, shifts, container sizes, lyophilizer loading and failed/aborted runs. | High | Sterile Manufacturers |  | No-Go |  | Not Started |  | 10 |  |  | Pending
RFI-048 | Sterile, Device & Packaging | Provide environmental-monitoring, sterility, bioburden and endotoxin trends with excursions, investigations and CAPA. | High | Sterile Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-049 | Sterile, Device & Packaging | Provide sterilization/depyrogenation, filter validation, integrity testing and PUPSIT rationale where applicable. | High | Sterile Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-050 | Sterile, Device & Packaging | Provide visible/subvisible particle controls, CCI method/validation through shelf life and transport, and glass/delamination risk. | High | Sterile Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-051 | Sterile, Device & Packaging | Provide E&L studies, toxicological assessments, container/component CoAs, silicone/tungsten and compatibility controls. | High | Sterile Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-052 | Sterile, Device & Packaging | Identify device/component manufacturers, ISO/device certificates, assembly site, dose-accuracy/human-factors evidence and complaint interface. | High | Device Chains |  | No-Go |  | Not Started |  | 10 |  |  | Pending
RFI-053 | Sterile, Device & Packaging | Provide packaging artwork, tamper evidence, serialization, label-control, reconciliation and South Africa configuration responsibilities. | Medium | Manufacturers |  | Pre-shipment |  | Not Started |  | 10 |  |  | Pending
RFI-054 | Stability, Cold Chain & Logistics | Provide ICH long-term, accelerated, stress, photostability and forced-degradation data for at least three representative batches. | High | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-055 | Stability, Cold Chain & Logistics | Provide bulk hold, freeze/thaw, in-use, reconstitution and shipping-excursion studies applicable to the proposed presentation. | High | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-056 | Stability, Cold Chain & Logistics | Define approved storage, transport range, excursion limits, decision tree, authorized disposition roles and stability data supporting each limit. | High | Manufacturers |  | Pre-shipment |  | Not Started |  | 10 |  |  | Pending
RFI-057 | Stability, Cold Chain & Logistics | Provide packaging qualification reports, thermal profiles, seasonal challenge, logger placement and failure-mode assessment. | High | Manufacturers |  | Pre-shipment |  | Not Started |  | 10 |  |  | Pending
RFI-058 | Stability, Cold Chain & Logistics | Design and execute a qualified Asia-to-South-Africa lane including customs-delay simulation, backup routing and receiving qualification. | High | Manufacturers |  | Pre-shipment |  | Not Started |  | 10 |  |  | Pending
RFI-059 | Stability, Cold Chain & Logistics | Provide carrier, freight forwarder, airline, customs broker, cold-store and last-mile qualification/audit records and quality agreements. | High | Manufacturers |  | Pre-shipment |  | Not Started |  | 10 |  |  | Pending
RFI-060 | Stability, Cold Chain & Logistics | Define tamper-evident seals, chain of custody, shipment IDs, calibrated logger controls, receipt checks and discrepancy escalation. | High | Manufacturers & Laboratories |  | Pre-shipment |  | Not Started |  | 10 |  |  | Pending
RFI-061 | Stability, Cold Chain & Logistics | Provide recall/returns/quarantine/destruction responsibilities and traceability exercise results for the proposed chain. | High | Manufacturers |  | Pre-shipment |  | Not Started |  | 10 |  |  | Pending
RFI-062 | South Africa & Commercial | Define proposed South African applicant/registration holder, importer, wholesaler/distributor and responsible quality/pharmacovigilance roles. | High | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-063 | South Africa & Commercial | Provide CTD/ASMF/CEP support plan, letters of access, deficiency-response support and inspection commitments. | High | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-064 | South Africa & Commercial | Confirm local testing/release, GDP storage, complaints, recalls, PV and change-notification responsibilities in the registered arrangement. | High | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-065 | South Africa & Commercial | Provide HS/tariff classification proposal, import permits/licences, Incoterms, insurance, customs documents and port/airport route. | Medium | Manufacturers |  | Pre-shipment |  | Not Started |  | 10 |  |  | Pending
RFI-066 | South Africa & Commercial | Provide pricing architecture, MOQ, lead time, capacity reservation, payment currency, price-adjustment formula and shortage-allocation terms. | Medium | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-067 | South Africa & Commercial | Accept audit rights, regulator access, source/subcontractor disclosure, prior change approval, recall support and full raw-data access. | High | Manufacturers & Laboratories |  | No-Go |  | Not Started |  | 10 |  |  | Pending
RFI-068 | South Africa & Commercial | Accept technology-transfer/exit assistance, alternate-site milestones, inventory floors, business-continuity obligations and termination rights. | High | Manufacturers |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-069 | Laboratory Qualification | Provide exact legal entity, site, controlled rooms/floors and current certificate with full method scope annex. | High | Laboratories |  | No-Go |  | Not Started |  | 10 |  |  | Pending
RFI-070 | Laboratory Qualification | Provide instrument inventory, model, software, qualification status, maintenance, calibration and redundancy for each proposed method. | High | Laboratories |  | Pre-audit |  | Not Started |  | 10 |  |  | Pending
RFI-071 | Laboratory Qualification | Provide analyst qualifications, method-specific experience and training records for peptide testing. | Medium | Laboratories |  | Pre-audit |  | Not Started |  | 10 |  |  | Pending
RFI-072 | Laboratory Qualification | Provide sample receipt, seal/temperature/weight checks, LIMS traceability, aliquot controls, storage, retains and destruction SOPs. | High | Laboratories |  | Pre-audit |  | Not Started |  | 10 |  |  | Pending
RFI-073 | Laboratory Qualification | Provide subcontractor list and agree no site/method transfer without prior written approval and requalification. | High | Laboratories |  | No-Go |  | Not Started |  | 10 |  |  | Pending
RFI-074 | Laboratory Qualification | Provide complete raw-data access and sponsor/regulator audit rights in the quality agreement. | High | Laboratories |  | No-Go |  | Not Started |  | 10 |  |  | Pending
RFI-075 | Laboratory Qualification | Execute blind split-sample testing on at least three representative lots under an approved comparability protocol. | High | Laboratories |  | Method Qualification |  | Not Started |  | 10 |  |  | Pending
RFI-076 | Laboratory Qualification | Investigate discordance using complete raw data; prohibit averaging away OOS and uncontrolled retest/resample. | High | Laboratories |  | Method Qualification |  | Not Started |  | 10 |  |  | Pending
RFI-077 | Laboratory Qualification | Provide stability chamber mapping, alarms, backup power, excursion records and disaster-recovery tests where stability work is proposed. | Medium | Laboratories |  | Pre-contract |  | Not Started |  | 10 |  |  | Pending
RFI-078 | Laboratory Qualification | Demonstrate successful method transfer/verification and issue a final method/site qualification report with restrictions and requalification triggers. | High | Laboratories |  | Method Qualification |  | Not Started |  | 10 |  |  | Pending
Formulas:
Days Outstanding = IF(OR([Status]="Closed",[Date Requested]=""),"",MAX(0,TODAY()-[Date Requested]))
Note on C9: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-001.
Note on D9: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-001.
Note on E9: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-001.
Note on F9: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-001.
Note on G9: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-001.
Note on H9: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-001.
Note on I9: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-001.
Note on J9: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-001.
Note on K9: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-001.
Note on L9: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-001.
Note on M9: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-001.
Note on O9: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-001.
Note on P9: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-001.
Note on Q9: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-001.
Note on S9: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-001.
Note on C10: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-002.
Note on D10: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-002.
Note on E10: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-002.
Note on F10: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-002.
Note on G10: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-002.
Note on H10: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-002.
Note on I10: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-002.
Note on J10: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-002.
Note on K10: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-002.
Note on L10: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-002.
Note on M10: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-002.
Note on O10: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-002.
Note on P10: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-002.
Note on Q10: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-002.
Note on S10: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-002.
Note on C11: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-003.
Note on D11: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-003.
Note on E11: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-003.
Note on F11: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-003.
Note on G11: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-003.
Note on H11: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-003.
Note on I11: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-003.
Note on J11: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-003.
Note on K11: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-003.
Note on L11: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-003.
Note on M11: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-003.
Note on O11: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-003.
Note on P11: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-003.
Note on Q11: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-003.
Note on S11: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-003.
Note on C12: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-004.
Note on D12: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-004.
Note on E12: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-004.
Note on F12: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-004.
Note on G12: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-004.
Note on H12: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-004.
Note on I12: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-004.
Note on J12: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-004.
Note on K12: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-004.
Note on L12: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-004.
Note on M12: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-004.
Note on O12: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-004.
Note on P12: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-004.
Note on Q12: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-004.
Note on S12: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-004.
Note on C13: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-005.
Note on D13: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-005.
Note on E13: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-005.
Note on F13: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-005.
Note on G13: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-005.
Note on H13: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-005.
Note on I13: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-005.
Note on J13: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-005.
Note on K13: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-005.
Note on L13: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-005.
Note on M13: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-005.
Note on O13: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-005.
Note on P13: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-005.
Note on Q13: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-005.
Note on S13: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-005.
Note on C14: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-006.
Note on D14: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-006.
Note on E14: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-006.
Note on F14: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-006.
Note on G14: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-006.
Note on H14: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-006.
Note on I14: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-006.
Note on J14: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-006.
Note on K14: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-006.
Note on L14: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-006.
Note on M14: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-006.
Note on O14: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-006.
Note on P14: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-006.
Note on Q14: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-006.
Note on S14: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-006.
Note on C15: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-007.
Note on D15: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-007.
Note on E15: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-007.
Note on F15: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-007.
Note on G15: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-007.
Note on H15: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-007.
Note on I15: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-007.
Note on J15: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-007.
Note on K15: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-007.
Note on L15: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-007.
Note on M15: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-007.
Note on O15: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-007.
Note on P15: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-007.
Note on Q15: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-007.
Note on S15: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-007.
Note on C16: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-008.
Note on D16: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-008.
Note on E16: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-008.
Note on F16: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-008.
Note on G16: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-008.
Note on H16: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-008.
Note on I16: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-008.
Note on J16: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-008.
Note on K16: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-008.
Note on L16: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-008.
Note on M16: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-008.
Note on O16: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-008.
Note on P16: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-008.
Note on Q16: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-008.
Note on S16: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-008.
Note on C17: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-009.
Note on D17: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-009.
Note on E17: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-009.
Note on F17: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-009.
Note on G17: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-009.
Note on H17: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-009.
Note on I17: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-009.
Note on J17: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-009.
Note on K17: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-009.
Note on L17: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-009.
Note on M17: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-009.
Note on O17: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-009.
Note on P17: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-009.
Note on Q17: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-009.
Note on S17: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-009.
Note on C18: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-010.
Note on D18: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-010.
Note on E18: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-010.
Note on F18: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-010.
Note on G18: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-010.
Note on H18: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-010.
Note on I18: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-010.
Note on J18: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-010.
Note on K18: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-010.
Note on L18: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-010.
Note on M18: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-010.
Note on O18: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-010.
Note on P18: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-010.
Note on Q18: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-010.
Note on S18: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-010.
Note on C19: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-011.
Note on D19: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-011.
Note on E19: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-011.
Note on F19: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-011.
Note on G19: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-011.
Note on H19: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-011.
Note on I19: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-011.
Note on J19: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-011.
Note on K19: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-011.
Note on L19: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-011.
Note on M19: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-011.
Note on O19: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-011.
Note on P19: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-011.
Note on Q19: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-011.
Note on S19: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-011.
Note on C20: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-012.
Note on D20: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-012.
Note on E20: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-012.
Note on F20: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-012.
Note on G20: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-012.
Note on H20: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-012.
Note on I20: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-012.
Note on J20: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-012.
Note on K20: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-012.
Note on L20: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-012.
Note on M20: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-012.
Note on O20: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-012.
Note on P20: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-012.
Note on Q20: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-012.
Note on S20: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-012.
Note on C21: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-013.
Note on D21: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-013.
Note on E21: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-013.
Note on F21: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-013.
Note on G21: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-013.
Note on H21: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-013.
Note on I21: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-013.
Note on J21: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-013.
Note on K21: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-013.
Note on L21: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-013.
Note on M21: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-013.
Note on O21: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-013.
Note on P21: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-013.
Note on Q21: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-013.
Note on S21: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-013.
Note on C22: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-014.
Note on D22: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-014.
Note on E22: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-014.
Note on F22: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-014.
Note on G22: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-014.
Note on H22: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-014.
Note on I22: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-014.
Note on J22: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-014.
Note on K22: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-014.
Note on L22: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-014.
Note on M22: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-014.
Note on O22: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-014.
Note on P22: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-014.
Note on Q22: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-014.
Note on S22: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-014.
Note on C23: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-015.
Note on D23: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-015.
Note on E23: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-015.
Note on F23: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-015.
Note on G23: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-015.
Note on H23: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-015.
Note on I23: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-015.
Note on J23: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-015.
Note on K23: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-015.
Note on L23: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-015.
Note on M23: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-015.
Note on O23: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-015.
Note on P23: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-015.
Note on Q23: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-015.
Note on S23: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-015.
Note on C24: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-016.
Note on D24: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-016.
Note on E24: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-016.
Note on F24: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-016.
Note on G24: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-016.
Note on H24: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-016.
Note on I24: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-016.
Note on J24: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-016.
Note on K24: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-016.
Note on L24: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-016.
Note on M24: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-016.
Note on O24: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-016.
Note on P24: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-016.
Note on Q24: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-016.
Note on S24: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-016.
Note on C25: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-017.
Note on D25: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-017.
Note on E25: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-017.
Note on F25: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-017.
Note on G25: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-017.
Note on H25: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-017.
Note on I25: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-017.
Note on J25: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-017.
Note on K25: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-017.
Note on L25: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-017.
Note on M25: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-017.
Note on O25: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-017.
Note on P25: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-017.
Note on Q25: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-017.
Note on S25: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-017.
Note on C26: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-018.
Note on D26: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-018.
Note on E26: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-018.
Note on F26: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-018.
Note on G26: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-018.
Note on H26: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-018.
Note on I26: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-018.
Note on J26: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-018.
Note on K26: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-018.
Note on L26: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-018.
Note on M26: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-018.
Note on O26: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-018.
Note on P26: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-018.
Note on Q26: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-018.
Note on S26: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-018.
Note on C27: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-019.
Note on D27: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-019.
Note on E27: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-019.
Note on F27: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-019.
Note on G27: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-019.
Note on H27: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-019.
Note on I27: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-019.
Note on J27: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-019.
Note on K27: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-019.
Note on L27: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-019.
Note on M27: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-019.
Note on O27: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-019.
Note on P27: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-019.
Note on Q27: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-019.
Note on S27: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-019.
Note on C28: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-020.
Note on D28: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-020.
Note on E28: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-020.
Note on F28: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-020.
Note on G28: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-020.
Note on H28: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-020.
Note on I28: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-020.
Note on J28: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-020.
Note on K28: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-020.
Note on L28: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-020.
Note on M28: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-020.
Note on O28: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-020.
Note on P28: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-020.
Note on Q28: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-020.
Note on S28: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-020.
Note on C29: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-021.
Note on D29: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-021.
Note on E29: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-021.
Note on F29: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-021.
Note on G29: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-021.
Note on H29: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-021.
Note on I29: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-021.
Note on J29: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-021.
Note on K29: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-021.
Note on L29: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-021.
Note on M29: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-021.
Note on O29: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-021.
Note on P29: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-021.
Note on Q29: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-021.
Note on S29: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-021.
Note on C30: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-022.
Note on D30: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-022.
Note on E30: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-022.
Note on F30: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-022.
Note on G30: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-022.
Note on H30: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-022.
Note on I30: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-022.
Note on J30: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-022.
Note on K30: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-022.
Note on L30: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-022.
Note on M30: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-022.
Note on O30: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-022.
Note on P30: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-022.
Note on Q30: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-022.
Note on S30: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-022.
Note on C31: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-023.
Note on D31: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-023.
Note on E31: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-023.
Note on F31: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-023.
Note on G31: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-023.
Note on H31: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-023.
Note on I31: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-023.
Note on J31: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-023.
Note on K31: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-023.
Note on L31: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-023.
Note on M31: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-023.
Note on O31: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-023.
Note on P31: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-023.
Note on Q31: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-023.
Note on S31: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-023.
Note on C32: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-024.
Note on D32: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-024.
Note on E32: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-024.
Note on F32: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-024.
Note on G32: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-024.
Note on H32: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-024.
Note on I32: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-024.
Note on J32: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-024.
Note on K32: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-024.
Note on L32: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-024.
Note on M32: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-024.
Note on O32: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-024.
Note on P32: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-024.
Note on Q32: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-024.
Note on S32: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-024.
Note on C33: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-025.
Note on D33: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-025.
Note on E33: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-025.
Note on F33: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-025.
Note on G33: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-025.
Note on H33: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-025.
Note on I33: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-025.
Note on J33: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-025.
Note on K33: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-025.
Note on L33: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-025.
Note on M33: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-025.
Note on O33: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-025.
Note on P33: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-025.
Note on Q33: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-025.
Note on S33: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-025.
Note on C34: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-026.
Note on D34: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-026.
Note on E34: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-026.
Note on F34: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-026.
Note on G34: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-026.
Note on H34: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-026.
Note on I34: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-026.
Note on J34: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-026.
Note on K34: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-026.
Note on L34: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-026.
Note on M34: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-026.
Note on O34: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-026.
Note on P34: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-026.
Note on Q34: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-026.
Note on S34: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-026.
Note on C35: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-027.
Note on D35: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-027.
Note on E35: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-027.
Note on F35: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-027.
Note on G35: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-027.
Note on H35: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-027.
Note on I35: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-027.
Note on J35: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-027.
Note on K35: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-027.
Note on L35: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-027.
Note on M35: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-027.
Note on O35: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-027.
Note on P35: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-027.
Note on Q35: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-027.
Note on S35: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-027.
Note on C36: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-028.
Note on D36: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-028.
Note on E36: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-028.
Note on F36: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-028.
Note on G36: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-028.
Note on H36: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-028.
Note on I36: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-028.
Note on J36: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-028.
Note on K36: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-028.
Note on L36: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-028.
Note on M36: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-028.
Note on O36: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-028.
Note on P36: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-028.
Note on Q36: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-028.
Note on S36: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-028.
Note on C37: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-029.
Note on D37: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-029.
Note on E37: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-029.
Note on F37: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-029.
Note on G37: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-029.
Note on H37: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-029.
Note on I37: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-029.
Note on J37: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-029.
Note on K37: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-029.
Note on L37: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-029.
Note on M37: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-029.
Note on O37: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-029.
Note on P37: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-029.
Note on Q37: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-029.
Note on S37: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-029.
Note on C38: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-030.
Note on D38: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-030.
Note on E38: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-030.
Note on F38: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-030.
Note on G38: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-030.
Note on H38: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-030.
Note on I38: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-030.
Note on J38: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-030.
Note on K38: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-030.
Note on L38: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-030.
Note on M38: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-030.
Note on O38: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-030.
Note on P38: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-030.
Note on Q38: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-030.
Note on S38: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-030.
Note on C39: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-031.
Note on D39: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-031.
Note on E39: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-031.
Note on F39: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-031.
Note on G39: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-031.
Note on H39: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-031.
Note on I39: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-031.
Note on J39: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-031.
Note on K39: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-031.
Note on L39: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-031.
Note on M39: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-031.
Note on O39: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-031.
Note on P39: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-031.
Note on Q39: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-031.
Note on S39: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-031.
Note on C40: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-032.
Note on D40: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-032.
Note on E40: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-032.
Note on F40: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-032.
Note on G40: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-032.
Note on H40: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-032.
Note on I40: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-032.
Note on J40: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-032.
Note on K40: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-032.
Note on L40: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-032.
Note on M40: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-032.
Note on O40: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-032.
Note on P40: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-032.
Note on Q40: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-032.
Note on S40: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-032.
Note on C41: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-033.
Note on D41: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-033.
Note on E41: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-033.
Note on F41: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-033.
Note on G41: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-033.
Note on H41: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-033.
Note on I41: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-033.
Note on J41: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-033.
Note on K41: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-033.
Note on L41: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-033.
Note on M41: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-033.
Note on O41: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-033.
Note on P41: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-033.
Note on Q41: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-033.
Note on S41: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-033.
Note on C42: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-034.
Note on D42: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-034.
Note on E42: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-034.
Note on F42: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-034.
Note on G42: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-034.
Note on H42: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-034.
Note on I42: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-034.
Note on J42: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-034.
Note on K42: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-034.
Note on L42: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-034.
Note on M42: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-034.
Note on O42: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-034.
Note on P42: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-034.
Note on Q42: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-034.
Note on S42: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-034.
Note on C43: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-035.
Note on D43: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-035.
Note on E43: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-035.
Note on F43: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-035.
Note on G43: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-035.
Note on H43: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-035.
Note on I43: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-035.
Note on J43: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-035.
Note on K43: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-035.
Note on L43: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-035.
Note on M43: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-035.
Note on O43: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-035.
Note on P43: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-035.
Note on Q43: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-035.
Note on S43: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-035.
Note on C44: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-036.
Note on D44: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-036.
Note on E44: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-036.
Note on F44: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-036.
Note on G44: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-036.
Note on H44: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-036.
Note on I44: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-036.
Note on J44: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-036.
Note on K44: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-036.
Note on L44: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-036.
Note on M44: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-036.
Note on O44: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-036.
Note on P44: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-036.
Note on Q44: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-036.
Note on S44: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-036.
Note on C45: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-037.
Note on D45: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-037.
Note on E45: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-037.
Note on F45: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-037.
Note on G45: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-037.
Note on H45: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-037.
Note on I45: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-037.
Note on J45: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-037.
Note on K45: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-037.
Note on L45: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-037.
Note on M45: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-037.
Note on O45: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-037.
Note on P45: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-037.
Note on Q45: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-037.
Note on S45: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-037.
Note on C46: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-038.
Note on D46: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-038.
Note on E46: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-038.
Note on F46: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-038.
Note on G46: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-038.
Note on H46: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-038.
Note on I46: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-038.
Note on J46: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-038.
Note on K46: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-038.
Note on L46: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-038.
Note on M46: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-038.
Note on O46: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-038.
Note on P46: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-038.
Note on Q46: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-038.
Note on S46: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-038.
Note on C47: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-039.
Note on D47: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-039.
Note on E47: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-039.
Note on F47: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-039.
Note on G47: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-039.
Note on H47: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-039.
Note on I47: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-039.
Note on J47: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-039.
Note on K47: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-039.
Note on L47: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-039.
Note on M47: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-039.
Note on O47: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-039.
Note on P47: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-039.
Note on Q47: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-039.
Note on S47: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-039.
Note on C48: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-040.
Note on D48: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-040.
Note on E48: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-040.
Note on F48: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-040.
Note on G48: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-040.
Note on H48: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-040.
Note on I48: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-040.
Note on J48: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-040.
Note on K48: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-040.
Note on L48: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-040.
Note on M48: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-040.
Note on O48: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-040.
Note on P48: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-040.
Note on Q48: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-040.
Note on S48: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-040.
Note on C49: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-041.
Note on D49: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-041.
Note on E49: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-041.
Note on F49: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-041.
Note on G49: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-041.
Note on H49: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-041.
Note on I49: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-041.
Note on J49: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-041.
Note on K49: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-041.
Note on L49: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-041.
Note on M49: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-041.
Note on O49: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-041.
Note on P49: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-041.
Note on Q49: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-041.
Note on S49: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-041.
Note on C50: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-042.
Note on D50: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-042.
Note on E50: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-042.
Note on F50: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-042.
Note on G50: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-042.
Note on H50: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-042.
Note on I50: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-042.
Note on J50: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-042.
Note on K50: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-042.
Note on L50: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-042.
Note on M50: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-042.
Note on O50: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-042.
Note on P50: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-042.
Note on Q50: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-042.
Note on S50: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-042.
Note on C51: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-043.
Note on D51: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-043.
Note on E51: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-043.
Note on F51: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-043.
Note on G51: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-043.
Note on H51: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-043.
Note on I51: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-043.
Note on J51: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-043.
Note on K51: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-043.
Note on L51: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-043.
Note on M51: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-043.
Note on O51: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-043.
Note on P51: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-043.
Note on Q51: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-043.
Note on S51: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-043.
Note on C52: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-044.
Note on D52: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-044.
Note on E52: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-044.
Note on F52: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-044.
Note on G52: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-044.
Note on H52: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-044.
Note on I52: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-044.
Note on J52: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-044.
Note on K52: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-044.
Note on L52: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-044.
Note on M52: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-044.
Note on O52: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-044.
Note on P52: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-044.
Note on Q52: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-044.
Note on S52: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-044.
Note on C53: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-045.
Note on D53: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-045.
Note on E53: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-045.
Note on F53: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-045.
Note on G53: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-045.
Note on H53: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-045.
Note on I53: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-045.
Note on J53: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-045.
Note on K53: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-045.
Note on L53: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-045.
Note on M53: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-045.
Note on O53: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-045.
Note on P53: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-045.
Note on Q53: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-045.
Note on S53: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-045.
Note on C54: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-046.
Note on D54: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-046.
Note on E54: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-046.
Note on F54: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-046.
Note on G54: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-046.
Note on H54: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-046.
Note on I54: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-046.
Note on J54: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-046.
Note on K54: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-046.
Note on L54: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-046.
Note on M54: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-046.
Note on O54: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-046.
Note on P54: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-046.
Note on Q54: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-046.
Note on S54: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-046.
Note on C55: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-047.
Note on D55: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-047.
Note on E55: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-047.
Note on F55: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-047.
Note on G55: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-047.
Note on H55: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-047.
Note on I55: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-047.
Note on J55: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-047.
Note on K55: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-047.
Note on L55: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-047.
Note on M55: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-047.
Note on O55: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-047.
Note on P55: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-047.
Note on Q55: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-047.
Note on S55: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-047.
Note on C56: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-048.
Note on D56: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-048.
Note on E56: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-048.
Note on F56: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-048.
Note on G56: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-048.
Note on H56: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-048.
Note on I56: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-048.
Note on J56: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-048.
Note on K56: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-048.
Note on L56: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-048.
Note on M56: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-048.
Note on O56: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-048.
Note on P56: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-048.
Note on Q56: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-048.
Note on S56: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-048.
Note on C57: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-049.
Note on D57: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-049.
Note on E57: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-049.
Note on F57: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-049.
Note on G57: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-049.
Note on H57: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-049.
Note on I57: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-049.
Note on J57: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-049.
Note on K57: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-049.
Note on L57: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-049.
Note on M57: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-049.
Note on O57: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-049.
Note on P57: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-049.
Note on Q57: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-049.
Note on S57: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-049.
Note on C58: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-050.
Note on D58: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-050.
Note on E58: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-050.
Note on F58: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-050.
Note on G58: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-050.
Note on H58: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-050.
Note on I58: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-050.
Note on J58: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-050.
Note on K58: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-050.
Note on L58: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-050.
Note on M58: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-050.
Note on O58: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-050.
Note on P58: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-050.
Note on Q58: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-050.
Note on S58: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-050.
Note on C59: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-051.
Note on D59: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-051.
Note on E59: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-051.
Note on F59: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-051.
Note on G59: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-051.
Note on H59: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-051.
Note on I59: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-051.
Note on J59: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-051.
Note on K59: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-051.
Note on L59: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-051.
Note on M59: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-051.
Note on O59: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-051.
Note on P59: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-051.
Note on Q59: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-051.
Note on S59: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-051.
Note on C60: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-052.
Note on D60: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-052.
Note on E60: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-052.
Note on F60: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-052.
Note on G60: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-052.
Note on H60: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-052.
Note on I60: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-052.
Note on J60: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-052.
Note on K60: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-052.
Note on L60: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-052.
Note on M60: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-052.
Note on O60: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-052.
Note on P60: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-052.
Note on Q60: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-052.
Note on S60: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-052.
Note on C61: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-053.
Note on D61: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-053.
Note on E61: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-053.
Note on F61: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-053.
Note on G61: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-053.
Note on H61: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-053.
Note on I61: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-053.
Note on J61: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-053.
Note on K61: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-053.
Note on L61: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-053.
Note on M61: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-053.
Note on O61: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-053.
Note on P61: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-053.
Note on Q61: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-053.
Note on S61: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-053.
Note on C62: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-054.
Note on D62: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-054.
Note on E62: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-054.
Note on F62: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-054.
Note on G62: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-054.
Note on H62: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-054.
Note on I62: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-054.
Note on J62: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-054.
Note on K62: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-054.
Note on L62: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-054.
Note on M62: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-054.
Note on O62: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-054.
Note on P62: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-054.
Note on Q62: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-054.
Note on S62: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-054.
Note on C63: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-055.
Note on D63: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-055.
Note on E63: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-055.
Note on F63: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-055.
Note on G63: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-055.
Note on H63: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-055.
Note on I63: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-055.
Note on J63: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-055.
Note on K63: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-055.
Note on L63: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-055.
Note on M63: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-055.
Note on O63: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-055.
Note on P63: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-055.
Note on Q63: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-055.
Note on S63: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-055.
Note on C64: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-056.
Note on D64: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-056.
Note on E64: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-056.
Note on F64: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-056.
Note on G64: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-056.
Note on H64: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-056.
Note on I64: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-056.
Note on J64: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-056.
Note on K64: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-056.
Note on L64: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-056.
Note on M64: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-056.
Note on O64: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-056.
Note on P64: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-056.
Note on Q64: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-056.
Note on S64: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-056.
Note on C65: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-057.
Note on D65: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-057.
Note on E65: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-057.
Note on F65: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-057.
Note on G65: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-057.
Note on H65: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-057.
Note on I65: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-057.
Note on J65: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-057.
Note on K65: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-057.
Note on L65: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-057.
Note on M65: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-057.
Note on O65: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-057.
Note on P65: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-057.
Note on Q65: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-057.
Note on S65: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-057.
Note on C66: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-058.
Note on D66: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-058.
Note on E66: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-058.
Note on F66: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-058.
Note on G66: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-058.
Note on H66: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-058.
Note on I66: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-058.
Note on J66: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-058.
Note on K66: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-058.
Note on L66: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-058.
Note on M66: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-058.
Note on O66: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-058.
Note on P66: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-058.
Note on Q66: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-058.
Note on S66: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-058.
Note on C67: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-059.
Note on D67: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-059.
Note on E67: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-059.
Note on F67: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-059.
Note on G67: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-059.
Note on H67: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-059.
Note on I67: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-059.
Note on J67: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-059.
Note on K67: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-059.
Note on L67: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-059.
Note on M67: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-059.
Note on O67: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-059.
Note on P67: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-059.
Note on Q67: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-059.
Note on S67: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-059.
Note on C68: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-060.
Note on D68: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-060.
Note on E68: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-060.
Note on F68: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-060.
Note on G68: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-060.
Note on H68: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-060.
Note on I68: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-060.
Note on J68: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-060.
Note on K68: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-060.
Note on L68: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-060.
Note on M68: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-060.
Note on O68: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-060.
Note on P68: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-060.
Note on Q68: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-060.
Note on S68: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-060.
Note on C69: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-061.
Note on D69: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-061.
Note on E69: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-061.
Note on F69: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-061.
Note on G69: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-061.
Note on H69: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-061.
Note on I69: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-061.
Note on J69: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-061.
Note on K69: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-061.
Note on L69: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-061.
Note on M69: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-061.
Note on O69: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-061.
Note on P69: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-061.
Note on Q69: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-061.
Note on S69: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-061.
Note on C70: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-062.
Note on D70: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-062.
Note on E70: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-062.
Note on F70: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-062.
Note on G70: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-062.
Note on H70: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-062.
Note on I70: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-062.
Note on J70: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-062.
Note on K70: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-062.
Note on L70: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-062.
Note on M70: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-062.
Note on O70: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-062.
Note on P70: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-062.
Note on Q70: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-062.
Note on S70: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-062.
Note on C71: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-063.
Note on D71: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-063.
Note on E71: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-063.
Note on F71: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-063.
Note on G71: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-063.
Note on H71: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-063.
Note on I71: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-063.
Note on J71: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-063.
Note on K71: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-063.
Note on L71: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-063.
Note on M71: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-063.
Note on O71: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-063.
Note on P71: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-063.
Note on Q71: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-063.
Note on S71: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-063.
Note on C72: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-064.
Note on D72: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-064.
Note on E72: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-064.
Note on F72: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-064.
Note on G72: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-064.
Note on H72: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-064.
Note on I72: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-064.
Note on J72: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-064.
Note on K72: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-064.
Note on L72: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-064.
Note on M72: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-064.
Note on O72: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-064.
Note on P72: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-064.
Note on Q72: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-064.
Note on S72: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-064.
Note on C73: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-065.
Note on D73: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-065.
Note on E73: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-065.
Note on F73: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-065.
Note on G73: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-065.
Note on H73: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-065.
Note on I73: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-065.
Note on J73: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-065.
Note on K73: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-065.
Note on L73: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-065.
Note on M73: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-065.
Note on O73: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-065.
Note on P73: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-065.
Note on Q73: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-065.
Note on S73: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-065.
Note on C74: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-066.
Note on D74: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-066.
Note on E74: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-066.
Note on F74: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-066.
Note on G74: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-066.
Note on H74: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-066.
Note on I74: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-066.
Note on J74: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-066.
Note on K74: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-066.
Note on L74: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-066.
Note on M74: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-066.
Note on O74: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-066.
Note on P74: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-066.
Note on Q74: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-066.
Note on S74: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-066.
Note on C75: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-067.
Note on D75: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-067.
Note on E75: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-067.
Note on F75: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-067.
Note on G75: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-067.
Note on H75: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-067.
Note on I75: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-067.
Note on J75: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-067.
Note on K75: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-067.
Note on L75: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-067.
Note on M75: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-067.
Note on O75: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-067.
Note on P75: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-067.
Note on Q75: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-067.
Note on S75: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-067.
Note on C76: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-068.
Note on D76: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-068.
Note on E76: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-068.
Note on F76: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-068.
Note on G76: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-068.
Note on H76: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-068.
Note on I76: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-068.
Note on J76: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-068.
Note on K76: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-068.
Note on L76: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-068.
Note on M76: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-068.
Note on O76: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-068.
Note on P76: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-068.
Note on Q76: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-068.
Note on S76: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-068.
Note on C77: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-069.
Note on D77: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-069.
Note on E77: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-069.
Note on F77: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-069.
Note on G77: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-069.
Note on H77: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-069.
Note on I77: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-069.
Note on J77: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-069.
Note on K77: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-069.
Note on L77: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-069.
Note on M77: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-069.
Note on O77: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-069.
Note on P77: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-069.
Note on Q77: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-069.
Note on S77: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-069.
Note on C78: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-070.
Note on D78: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-070.
Note on E78: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-070.
Note on F78: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-070.
Note on G78: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-070.
Note on H78: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-070.
Note on I78: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-070.
Note on J78: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-070.
Note on K78: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-070.
Note on L78: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-070.
Note on M78: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-070.
Note on O78: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-070.
Note on P78: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-070.
Note on Q78: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-070.
Note on S78: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-070.
Note on C79: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-071.
Note on D79: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-071.
Note on E79: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-071.
Note on F79: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-071.
Note on G79: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-071.
Note on H79: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-071.
Note on I79: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-071.
Note on J79: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-071.
Note on K79: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-071.
Note on L79: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-071.
Note on M79: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-071.
Note on O79: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-071.
Note on P79: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-071.
Note on Q79: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-071.
Note on S79: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-071.
Note on C80: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-072.
Note on D80: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-072.
Note on E80: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-072.
Note on F80: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-072.
Note on G80: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-072.
Note on H80: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-072.
Note on I80: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-072.
Note on J80: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-072.
Note on K80: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-072.
Note on L80: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-072.
Note on M80: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-072.
Note on O80: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-072.
Note on P80: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-072.
Note on Q80: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-072.
Note on S80: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-072.
Note on C81: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-073.
Note on D81: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-073.
Note on E81: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-073.
Note on F81: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-073.
Note on G81: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-073.
Note on H81: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-073.
Note on I81: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-073.
Note on J81: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-073.
Note on K81: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-073.
Note on L81: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-073.
Note on M81: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-073.
Note on O81: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-073.
Note on P81: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-073.
Note on Q81: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-073.
Note on S81: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-073.
Note on C82: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-074.
Note on D82: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-074.
Note on E82: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-074.
Note on F82: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-074.
Note on G82: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-074.
Note on H82: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-074.
Note on I82: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-074.
Note on J82: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-074.
Note on K82: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-074.
Note on L82: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-074.
Note on M82: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-074.
Note on O82: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-074.
Note on P82: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-074.
Note on Q82: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-074.
Note on S82: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-074.
Note on C83: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-075.
Note on D83: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-075.
Note on E83: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-075.
Note on F83: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-075.
Note on G83: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-075.
Note on H83: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-075.
Note on I83: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-075.
Note on J83: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-075.
Note on K83: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-075.
Note on L83: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-075.
Note on M83: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-075.
Note on O83: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-075.
Note on P83: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-075.
Note on Q83: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-075.
Note on S83: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-075.
Note on C84: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-076.
Note on D84: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-076.
Note on E84: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-076.
Note on F84: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-076.
Note on G84: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-076.
Note on H84: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-076.
Note on I84: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-076.
Note on J84: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-076.
Note on K84: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-076.
Note on L84: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-076.
Note on M84: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-076.
Note on O84: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-076.
Note on P84: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-076.
Note on Q84: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-076.
Note on S84: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-076.
Note on C85: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-077.
Note on D85: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-077.
Note on E85: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-077.
Note on F85: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-077.
Note on G85: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-077.
Note on H85: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-077.
Note on I85: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-077.
Note on J85: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-077.
Note on K85: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-077.
Note on L85: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-077.
Note on M85: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-077.
Note on O85: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-077.
Note on P85: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-077.
Note on Q85: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-077.
Note on S85: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-077.
Note on C86: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-078.
Note on D86: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-078.
Note on E86: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-078.
Note on F86: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-078.
Note on G86: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-078.
Note on H86: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-078.
Note on I86: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-078.
Note on J86: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-078.
Note on K86: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-078.
Note on L86: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-078.
Note on M86: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-078.
Note on O86: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-078.
Note on P86: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-078.
Note on Q86: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-078.
Note on S86: Source: Final report sections 11-15 and 16 Decision date: 20 August 2026 Context: Pre-populated diligence request RFI-078.

## 90-Day Plan
Ninety-Day Supplier Qualification Programme
Cross-functional documentary review, technical assessment, audit, laboratory qualification, CAPA and board disposition
No purchase or release while a critical/no-go item remains open
Phase | Timing | Activity | Primary Owner | Inputs | Deliverable | Gate | Status | Target Date | Actual Date | Evidence / Decision Note
1 | Days 0–10 | Freeze product target profile, dosage form, annual demand, registered-market strategy and evidence requirements; issue NDAs and RFIs. | Project Lead / Regulatory | Target product profile and forecast | Approved requirement and one exact proposed chain per supplier | RFI Approved | Not Started
2 | Days 11–25 | Verify legal entities, licences, regulator records, dossier references, sanctions/export constraints and adverse-history packages. | Regulatory / Quality / Legal | RFI responses and primary records | Document-completeness score and reject/advance list | Document Gate | Not Started
3 | Days 26–40 | Review route, scale, PPQ/CPV, impurity strategy, analytical/stability data, cleaning and sterile/device evidence. | Technical / Quality | Technical document room | Product/site technical risk assessment and audit agenda | Technical Gate | Not Started
4 | Days 41–55 | Assess material genealogy, capacity, subcontractors, BCP, cold chain, South Africa lane and quality-agreement redlines. | Supply / Quality / Commercial | Supplier map, capacity and logistics data | Approved dependency map and preliminary SAHPRA gap assessment | Supply Gate | Not Started
5 | Days 56–70 | Conduct risk-based on-site audits of proposed API and drug-product sites; review native data and adverse cases. | Lead Auditor / SMEs | Audit plan and document room | Critical/major/other findings and preliminary disposition | Audit Gate | Not Started
6 | Days 61–78 | Audit laboratories and run blind split-sample method exercise in parallel. | QC / Laboratory Lead | Approved protocol and three lots | Method/site comparability, custody and raw-data assessment | Method Gate | Not Started
7 | Days 71–85 | Review supplier/laboratory CAPA, close quality/technical agreements and confirm effectiveness plans. | Quality / Legal / Supply | CAPA and agreement redlines | No critical open finding; acceptable owners/dates/effectiveness | CAPA Gate | Not Started
8 | Days 86–90 | Cross-functional quality, regulatory, supply, legal and commercial decision board; re-score from verified evidence. | Steering Committee | Complete diligence file | Conditional shortlist, hold or no-go with expiry/reassessment date | Board Decision | Not Started
AUDIT SAMPLING MINIMUM
Sample | Audit expectation
Recent release batch | Trace from materials and approved vendors through production, testing, release, storage and distribution.
Deviation or OOS batch | Review original data, hypothesis, root cause, retest/resample, impact, CAPA and recurrence.
Reworked/reprocessed or low-yield batch | Confirm authorization, scientific rationale, impurity impact and dossier consistency.
Stability OOT or complaint case | Review trend rules, escalation, product impact, notification and CAPA.
Cleaning-validation run | Confirm worst case, HBEL, recovery, sampling, shared equipment and continued verification.
Supplier/material change | Trace qualification, comparability, change control, dossier impact and customer approval.
Sterile additions | One failed/aborted APS if any, one EM action event, and one CCI or particulate investigation.
Note on C9: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 1.
Note on D9: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 1.
Note on E9: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 1.
Note on F9: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 1.
Note on G9: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 1.
Note on H9: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 1.
Note on I9: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 1.
Note on J9: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable phase status.
Note on K9: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on L9: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable actual date.
Note on M9: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable decision note.
Note on C10: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 2.
Note on D10: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 2.
Note on E10: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 2.
Note on F10: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 2.
Note on G10: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 2.
Note on H10: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 2.
Note on I10: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 2.
Note on J10: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable phase status.
Note on K10: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on L10: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable actual date.
Note on M10: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable decision note.
Note on C11: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 3.
Note on D11: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 3.
Note on E11: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 3.
Note on F11: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 3.
Note on G11: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 3.
Note on H11: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 3.
Note on I11: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 3.
Note on J11: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable phase status.
Note on K11: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on L11: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable actual date.
Note on M11: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable decision note.
Note on C12: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 4.
Note on D12: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 4.
Note on E12: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 4.
Note on F12: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 4.
Note on G12: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 4.
Note on H12: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 4.
Note on I12: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 4.
Note on J12: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable phase status.
Note on K12: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on L12: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable actual date.
Note on M12: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable decision note.
Note on C13: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 5.
Note on D13: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 5.
Note on E13: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 5.
Note on F13: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 5.
Note on G13: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 5.
Note on H13: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 5.
Note on I13: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 5.
Note on J13: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable phase status.
Note on K13: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on L13: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable actual date.
Note on M13: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable decision note.
Note on C14: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 6.
Note on D14: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 6.
Note on E14: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 6.
Note on F14: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 6.
Note on G14: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 6.
Note on H14: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 6.
Note on I14: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 6.
Note on J14: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable phase status.
Note on K14: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on L14: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable actual date.
Note on M14: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable decision note.
Note on C15: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 7.
Note on D15: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 7.
Note on E15: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 7.
Note on F15: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 7.
Note on G15: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 7.
Note on H15: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 7.
Note on I15: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 7.
Note on J15: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable phase status.
Note on K15: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on L15: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable actual date.
Note on M15: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable decision note.
Note on C16: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 8.
Note on D16: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 8.
Note on E16: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 8.
Note on F16: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 8.
Note on G16: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 8.
Note on H16: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 8.
Note on I16: Source: Final report section 12 Decision date: 20 August 2026 Context: Qualification phase 8.
Note on J16: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable phase status.
Note on K16: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on L16: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable actual date.
Note on M16: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable decision note.
Note on C22: Source: Final report section 12 Decision date: 20 August 2026 Context: Risk-based audit sampling.
Note on D22: Source: Final report section 12 Decision date: 20 August 2026 Context: Risk-based audit sampling.
Note on C23: Source: Final report section 12 Decision date: 20 August 2026 Context: Risk-based audit sampling.
Note on D23: Source: Final report section 12 Decision date: 20 August 2026 Context: Risk-based audit sampling.
Note on C24: Source: Final report section 12 Decision date: 20 August 2026 Context: Risk-based audit sampling.
Note on D24: Source: Final report section 12 Decision date: 20 August 2026 Context: Risk-based audit sampling.
Note on C25: Source: Final report section 12 Decision date: 20 August 2026 Context: Risk-based audit sampling.
Note on D25: Source: Final report section 12 Decision date: 20 August 2026 Context: Risk-based audit sampling.
Note on C26: Source: Final report section 12 Decision date: 20 August 2026 Context: Risk-based audit sampling.
Note on D26: Source: Final report section 12 Decision date: 20 August 2026 Context: Risk-based audit sampling.
Note on C27: Source: Final report section 12 Decision date: 20 August 2026 Context: Risk-based audit sampling.
Note on D27: Source: Final report section 12 Decision date: 20 August 2026 Context: Risk-based audit sampling.
Note on C28: Source: Final report section 12 Decision date: 20 August 2026 Context: Risk-based audit sampling.
Note on D28: Source: Final report section 12 Decision date: 20 August 2026 Context: Risk-based audit sampling.

## Risk & No-Go
Supply-Chain Risk Register and No-Go Gates
Risks are product-, site-, method- and lane-specific; numeric score never overrides a no-go condition
Disposition: Monitor / Conditional Hold / No-Go / Closed
Risk ID | Domain | Risk / Failure Mode | Impacted Scope | Likelihood | Impact | Current Evidence | Required Mitigation | Owner | Disposition | Target Date | Evidence / Closure Note
R-001 | Regulatory | No SAHPRA registration, site recognition or dossier linkage established. | All proposed chains | High | Critical | Unknown for every manufacturer. | Commission South African regulatory gap assessment and fix applicant/importer/licence/dossier chain. | Regulatory | Conditional Hold
R-002 | Legal site | Contract, licence, dossier and actual physical site do not match. | Manufacturer or laboratory | Medium | Critical | Public records incomplete for several entities. | Reconcile legal entity, address, building, line, activity and authorized scope. | Legal / Quality | No-Go
R-003 | Data integrity | Native electronic data or audit trails are refused, altered, selectively deleted or incomplete. | All quality decisions | Medium | Critical | Public DI evidence is weak. | Contract raw-data rights; audit systems, roles, metadata, reintegration and backups. | Quality | No-Go
R-004 | Subcontracting | Undisclosed manufacturing, testing, sterilization, device, storage or logistics subcontractor. | All proposed chains | High | Critical | Public subcontract maps are generally absent. | Named schedule, prior approval, audit rights and no further subcontracting. | Quality / Supply | No-Go
R-005 | Raw materials | Critical amino acid, resin/linker, side chain or reagent manufacturer/country cannot be identified. | Peptide API | High | Critical | Origin and dual-source status generally unknown. | Complete genealogy, risk assessment, second-source plan and safety stock. | Supply / Technical | No-Go
R-006 | Single site | Only one validated API or sterile site/train is available. | Most candidates | High | High | Site concentration is widespread. | BCP evidence, alternate-site milestone, transfer rights, buffer stock and RTO. | Supply | Conditional Hold
R-007 | Cold chain | No qualified Asia-to-South-Africa lane or customs-delay simulation. | Temperature-sensitive material | High | Critical | Not publicly evidenced for any candidate. | Seasonal lane qualification, loggers, backup carrier and excursion decision tree. | Logistics / Quality | Conditional Hold
R-008 | Process validation | PPQ/CPV or equipment qualification is incomplete or adverse history is unresolved. | CPC, Piramal and others | Medium | Critical | Public 483/VAI history exists. | Review full inspection packages, PPQ/CPV, CAPA effectiveness and recurrence. | Technical / Quality | Conditional Hold
R-009 | Cleaning | Shared-equipment carryover/cleaning validation is inadequate. | Multi-product API sites | Medium | Critical | Specific FDA concern at Piramal/CPC-related histories. | HBEL-based cleaning validation, worst-case selection and ongoing verification. | Quality | No-Go
R-010 | Sterility assurance | CCS, APS, EM, sterilization/depyrogenation, CCI or particle evidence is inadequate. | Sterile finished dose | Medium | Critical | Public sterile evidence incomplete. | Separate sterile-site audit and full assurance package. | Sterile SME | No-Go
R-011 | Device chain | Component makers, assembly site, dose accuracy or complaint interface are opaque. | PFS/pen/autoinjector | High | High | Hybio/Scino device chains require disclosure. | Map components and responsibilities; verify device/combination-product controls. | Device SME | Conditional Hold
R-012 | Laboratory scope | Accreditation or licence does not cover the exact site/method/matrix. | Independent testing | High | Critical | All four labs have scope gaps; Intertek current scope is non-pharma. | Obtain full scope annex, audit and method-by-method qualification. | QC Lead | Conditional Hold
R-013 | OOS governance | Supplier or laboratory tests into compliance or averages away an OOS. | Release testing | Medium | Critical | Public procedures unavailable; Vimta nuance requires review. | Quality agreement, case review, raw-data rights and sponsor approval before retest/resample. | Quality | No-Go
R-014 | Adverse event | Open OAI/import restriction/licence suspension applies to the proposed chain. | Site/product specific | Medium | Critical | Several historical events require current status. | Direct regulator verification and accepted closure before progression. | Regulatory / Quality | No-Go
R-015 | Governance | False disclosure, delayed reporting or weak quality governance undermines trust. | Sinopep, Hybio and others | Medium | High | Public governance events identified. | Board remediation, DI-focused audit and record reconciliation. | Legal / Quality | Conditional Hold
R-016 | Capacity | Purification/lyophilization bottleneck, high utilization or unreserved capacity causes shortage. | Peptide API | High | High | Headline reactor capacity may overstate released output. | Normalize saleable throughput, reserve capacity and qualify alternate train/site. | Supply / Technical | Conditional Hold
R-017 | Geopolitical | Sanctions, export controls, cross-strait/China concentration, payment or insurance disruption. | China/Taiwan-linked chains | Medium | High | Material external uncertainty. | Legal monitoring, alternate geography, insurance, exit and transfer clauses. | Legal / Supply | Monitor
R-018 | Change control | Unapproved site, route, raw material, test, device or packaging change conflicts with dossier. | All chains | Medium | Critical | Public commitments incomplete. | Prior written approval, regulatory impact assessment and dossier/change governance. | Regulatory / Quality | No-Go
R-019 | Research material | Research/non-GMP or brokered material enters therapeutic manufacture. | All therapeutic products | Low | Critical | Several groups offer research services. | Explicit segregation, batch genealogy and contract prohibition. | Quality | No-Go
R-020 | Traceability | Recall, returns, quarantine or shipment traceability cannot identify every batch and handoff. | South Africa distribution | Medium | Critical | No candidate SA lane tested. | End-to-end mock recall and shipment trace before first commercial supply. | Quality / Logistics | Conditional Hold
Note on C9: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-001.
Note on D9: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-001.
Note on E9: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-001.
Note on F9: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-001.
Note on G9: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-001.
Note on H9: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-001.
Note on I9: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-001.
Note on J9: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-001.
Note on K9: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-001.
Note on L9: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-001.
Note on M9: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on N9: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable closure note.
Note on C10: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-002.
Note on D10: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-002.
Note on E10: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-002.
Note on F10: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-002.
Note on G10: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-002.
Note on H10: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-002.
Note on I10: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-002.
Note on J10: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-002.
Note on K10: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-002.
Note on L10: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-002.
Note on M10: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on N10: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable closure note.
Note on C11: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-003.
Note on D11: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-003.
Note on E11: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-003.
Note on F11: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-003.
Note on G11: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-003.
Note on H11: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-003.
Note on I11: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-003.
Note on J11: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-003.
Note on K11: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-003.
Note on L11: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-003.
Note on M11: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on N11: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable closure note.
Note on C12: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-004.
Note on D12: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-004.
Note on E12: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-004.
Note on F12: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-004.
Note on G12: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-004.
Note on H12: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-004.
Note on I12: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-004.
Note on J12: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-004.
Note on K12: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-004.
Note on L12: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-004.
Note on M12: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on N12: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable closure note.
Note on C13: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-005.
Note on D13: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-005.
Note on E13: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-005.
Note on F13: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-005.
Note on G13: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-005.
Note on H13: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-005.
Note on I13: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-005.
Note on J13: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-005.
Note on K13: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-005.
Note on L13: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-005.
Note on M13: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on N13: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable closure note.
Note on C14: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-006.
Note on D14: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-006.
Note on E14: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-006.
Note on F14: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-006.
Note on G14: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-006.
Note on H14: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-006.
Note on I14: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-006.
Note on J14: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-006.
Note on K14: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-006.
Note on L14: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-006.
Note on M14: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on N14: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable closure note.
Note on C15: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-007.
Note on D15: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-007.
Note on E15: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-007.
Note on F15: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-007.
Note on G15: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-007.
Note on H15: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-007.
Note on I15: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-007.
Note on J15: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-007.
Note on K15: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-007.
Note on L15: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-007.
Note on M15: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on N15: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable closure note.
Note on C16: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-008.
Note on D16: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-008.
Note on E16: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-008.
Note on F16: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-008.
Note on G16: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-008.
Note on H16: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-008.
Note on I16: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-008.
Note on J16: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-008.
Note on K16: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-008.
Note on L16: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-008.
Note on M16: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on N16: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable closure note.
Note on C17: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-009.
Note on D17: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-009.
Note on E17: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-009.
Note on F17: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-009.
Note on G17: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-009.
Note on H17: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-009.
Note on I17: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-009.
Note on J17: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-009.
Note on K17: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-009.
Note on L17: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-009.
Note on M17: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on N17: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable closure note.
Note on C18: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-010.
Note on D18: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-010.
Note on E18: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-010.
Note on F18: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-010.
Note on G18: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-010.
Note on H18: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-010.
Note on I18: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-010.
Note on J18: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-010.
Note on K18: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-010.
Note on L18: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-010.
Note on M18: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on N18: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable closure note.
Note on C19: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-011.
Note on D19: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-011.
Note on E19: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-011.
Note on F19: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-011.
Note on G19: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-011.
Note on H19: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-011.
Note on I19: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-011.
Note on J19: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-011.
Note on K19: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-011.
Note on L19: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-011.
Note on M19: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on N19: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable closure note.
Note on C20: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-012.
Note on D20: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-012.
Note on E20: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-012.
Note on F20: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-012.
Note on G20: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-012.
Note on H20: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-012.
Note on I20: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-012.
Note on J20: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-012.
Note on K20: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-012.
Note on L20: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-012.
Note on M20: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on N20: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable closure note.
Note on C21: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-013.
Note on D21: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-013.
Note on E21: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-013.
Note on F21: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-013.
Note on G21: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-013.
Note on H21: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-013.
Note on I21: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-013.
Note on J21: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-013.
Note on K21: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-013.
Note on L21: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-013.
Note on M21: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on N21: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable closure note.
Note on C22: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-014.
Note on D22: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-014.
Note on E22: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-014.
Note on F22: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-014.
Note on G22: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-014.
Note on H22: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-014.
Note on I22: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-014.
Note on J22: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-014.
Note on K22: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-014.
Note on L22: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-014.
Note on M22: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on N22: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable closure note.
Note on C23: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-015.
Note on D23: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-015.
Note on E23: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-015.
Note on F23: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-015.
Note on G23: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-015.
Note on H23: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-015.
Note on I23: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-015.
Note on J23: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-015.
Note on K23: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-015.
Note on L23: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-015.
Note on M23: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on N23: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable closure note.
Note on C24: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-016.
Note on D24: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-016.
Note on E24: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-016.
Note on F24: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-016.
Note on G24: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-016.
Note on H24: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-016.
Note on I24: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-016.
Note on J24: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-016.
Note on K24: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-016.
Note on L24: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-016.
Note on M24: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on N24: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable closure note.
Note on C25: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-017.
Note on D25: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-017.
Note on E25: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-017.
Note on F25: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-017.
Note on G25: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-017.
Note on H25: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-017.
Note on I25: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-017.
Note on J25: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-017.
Note on K25: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-017.
Note on L25: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-017.
Note on M25: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on N25: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable closure note.
Note on C26: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-018.
Note on D26: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-018.
Note on E26: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-018.
Note on F26: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-018.
Note on G26: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-018.
Note on H26: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-018.
Note on I26: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-018.
Note on J26: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-018.
Note on K26: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-018.
Note on L26: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-018.
Note on M26: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on N26: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable closure note.
Note on C27: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-019.
Note on D27: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-019.
Note on E27: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-019.
Note on F27: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-019.
Note on G27: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-019.
Note on H27: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-019.
Note on I27: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-019.
Note on J27: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-019.
Note on K27: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-019.
Note on L27: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-019.
Note on M27: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on N27: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable closure note.
Note on C28: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-020.
Note on D28: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-020.
Note on E28: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-020.
Note on F28: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-020.
Note on G28: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-020.
Note on H28: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-020.
Note on I28: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-020.
Note on J28: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-020.
Note on K28: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-020.
Note on L28: Source: Final report sections 6, 9, 13 and 16 Decision date: 20 August 2026 Context: Risk register item R-020.
Note on M28: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable target date.
Note on N28: Source: User-controlled diligence field Decision date: 20 August 2026 Context: Editable closure note.

## Source Register
Research Source Register
Complete source inventory extracted from discovery, ten manufacturer dossiers and four laboratory dossiers
301 unique URLs ¦ Access and content may change; archive primary evidence in the controlled data room
Source ID | Category | Entity / Dossier | Source File | URL | Review Cutoff | Evidence Note
SRC-001 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://www.fda.gov/drugs/drug-approvals-and-databases/drug-establishments-current-registration-site-decrs | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-002 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://tides.wuxiapptec.com/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-003 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://tides.wuxiapptec.com/wuxi-apptecs-changzhou-and-taixing-api-sites-successfully-pass-fda-inspections/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-004 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://www.sinopep.com/quotation/gmp-peptides/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-005 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://www.fda.gov/media/190915/download | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-006 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://www.fda.gov/media/183518/download | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-007 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://www.hybio.com/about-us/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-008 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://www.fda.gov/media/148286/download | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-009 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://cpcscientific.com/custom-peptide-synthesis/cgmp-peptide-manufacturing/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-010 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://www.fda.gov/media/178556/download | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-011 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://www.fda.gov/media/181469/download | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-012 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://www.piramalpharmasolutions.com/specialized-offerings/peptides-api | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-013 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://shilpapharma.com/peptide-cdmo-services/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-014 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://peptistar.com/en/company/message/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-015 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://www.amed.go.jp/en/news/release_20191206.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-016 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://ajibio-pharma.ajinomoto.com/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-017 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://hlbpep.co.kr/eng/peptides/gmp.php | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-018 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://www.scinopharm.com/solutions/SPTCMC/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-019 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://www.scinopharm.com/news-detail/113/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-020 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://www.sgs.com/en-us/news/2024/10/shanghai-health-science-lab-passes-us-fda-inspection | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-021 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://www.sgsgroup.com.cn/en-cn/services/pharmaceutical-microbiology-testing | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-022 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://location.eurofins.com/en/ele/eurofins-analytical-science-laboratories-inc/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-023 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://www.eurofins.com/en/media-centre/press-releases/2018-05-22/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-024 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://vimta.com/wp-content/uploads/2026/05/Latest-NABL-Certificate-2026.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-025 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://vimta.com/wp-content/uploads/2026/05/DCA-Licence-Renewal.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-026 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://vimta.com/about-us/accreditations/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-027 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://www.intertek.com/pharmaceutical/mumbai-india/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-028 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://nabl-india.org/nabl/file_download1.php?filename=202404180952-TC-5663-doc.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-029 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | http://www.neulandlabs.com/en/about-us/our-facilities/peptide-manufacturing-facility-hyderabad | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-030 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | http://www.peptron.com/ds3_4_1.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-031 | Discovery | Discovery universe | /home/ubuntu/george_asia_peptide_due_diligence/discovery.md | https://www.fda.gov/inspections-compliance-enforcement-and-criminal-investigations/warning-letters/auriga-research-pvt-ltd-730694-08122026 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-032 | Manufacturer | 01-M01 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/01-M01.md | https://www.hkexnews.hk/listedco/listconews/sehk/2026/0323/2026032300516.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-033 | Manufacturer | 01-M01 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/01-M01.md | https://tides.wuxiapptec.com/services-solutions/peptide/peptide-cmc/drug-product/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-034 | Manufacturer | 01-M01 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/01-M01.md | https://sta.wuxiapptec.com/wuxi-apptecs-changzhou-and-taixing-api-sites-successfully-pass-fda-inspections/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-035 | Manufacturer | 01-M01 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/01-M01.md | https://tides.wuxiapptec.com/facility/changzhou-china/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-036 | Manufacturer | 01-M01 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/01-M01.md | https://sta.wuxiapptec.com/wuxi-sta-successfully-passes-four-pre-approval-inspections-by-south-koreas-ministry-of-food-and-drug-safety-at-three-manufacturing-sites-in-china/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-037 | Manufacturer | 01-M01 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/01-M01.md | https://www.fda.gov/drugs/guidance-compliance-regulatory-information/wuxi-sta-pharmaceutical-co-ltd-3032023 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-038 | Manufacturer | 01-M01 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/01-M01.md | https://sta.wuxiapptec.com/wuxi-sta-passes-the-first-ema-drug-product-pre-approval-inspection-at-its-wuxi-city-site/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-039 | Manufacturer | 01-M01 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/01-M01.md | https://tides.wuxiapptec.com/services-solutions/peptide/peptide-cmc/api/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-040 | Manufacturer | 01-M01 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/01-M01.md | https://tides.wuxiapptec.com/wuxi-apptec-triples-peptide-manufacturing-capacity-and-launches-the-new-taixing-api-manufacturing-site/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-041 | Manufacturer | 01-M01 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/01-M01.md | https://www.federalregister.gov/documents/2026/06/10/2026-11571/notice-of-availability-of-designation-of-chinese-military-companies | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-042 | Manufacturer | 01-M01 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/01-M01.md | https://law.justia.com/cases/federal/district-courts/district-of-columbia/dcdce/1:2026cv02069/293402/25/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-043 | Manufacturer | 01-M01 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/01-M01.md | https://www.wuxiapptec.com/news/wuxi-news/wuxi-apptecs-sta-subsidiary-opens-new-campus-in-changzhou | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-044 | Manufacturer | 01-M01 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/01-M01.md | https://job.lzu.edu.cn/html/22/article/2021/26785.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-045 | Manufacturer | 01-M01 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/01-M01.md | https://www.taixing.gov.cn/zwgk/xxgk/qt/art/2026/art_36ffc717d971456e810a5c5f09c3cab5.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-046 | Manufacturer | 01-M01 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/01-M01.md | https://www.fda.gov/inspections-compliance-enforcement-and-criminal-investigations/inspection-classification-database | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-047 | Manufacturer | 01-M01 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/01-M01.md | https://tides.wuxiapptec.com/services-solutions/peptide/peptide-cmc/analytical/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-048 | Manufacturer | 01-M01 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/01-M01.md | https://officialsite-static.wuxiapptec.com/upload/ANNOUNCEMENT_FOR_PRELIMINARY_INJUNCTION_2e0a0bc090.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-049 | Manufacturer | 01-M01 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/01-M01.md | https://tides.wuxiapptec.com/facility/taixing-china/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-050 | Manufacturer | 01-M01 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/01-M01.md | https://tides.wuxiapptec.com/facility/wuxi-city-china/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-051 | Manufacturer | 02-M02 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/02-M02.md | http://static.cninfo.com.cn/finalpage/2026-04-30/1225262826.PDF | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-052 | Manufacturer | 02-M02 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/02-M02.md | http://star.sse.com.cn/star/en/marketdata/snapshot/c/5547483.shtml | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-053 | Manufacturer | 02-M02 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/02-M02.md | https://www.accessdata.fda.gov/scripts/SDA/sdDetailNavigation.cfm?sd=srolist&id=587C873A8EF03E9EE06346F0E10A144F&rownum=1997 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-054 | Manufacturer | 02-M02 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/02-M02.md | https://www.allsino.com/en/index.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-055 | Manufacturer | 02-M02 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/02-M02.md | https://www.sinopep.com/cdmo-services/formulation/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-056 | Manufacturer | 02-M02 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/02-M02.md | https://www.fda.gov/media/85138/download | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-057 | Manufacturer | 02-M02 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/02-M02.md | https://www.sinopep.com/cdmo-services/regulatory-affairs/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-058 | Manufacturer | 02-M02 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/02-M02.md | https://www.csrc.gov.cn/csrc/c101928/c7603410/content.shtml | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-059 | Manufacturer | 02-M02 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/02-M02.md | https://www.medtideinc.com/tc/CompanyNews/info.aspx?itemid=318 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-060 | Manufacturer | 02-M02 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/02-M02.md | https://www.medtideinc.com/tc/companynews/info.aspx?itemid=319 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-061 | Manufacturer | 02-M02 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/02-M02.md | http://www.csrc.gov.cn/csrc/c100090/c1519459/1519459/files/%E5%8F%91%E8%A1%8C%E4%BA%BA%E5%8F%8A%E4%BF%9D%E8%8D%90%E6%9C%BA%E6%9E%84%E5%85%B3%E4%BA%8E%E5%8F%91%E8%A1%8C%E6%B3%A8%E5%86%8C%E7%8E%AF%E8%8A%82%E5%8F%8D%E9%A6%88%E6%84%8F%E8%A7%81%E8%90%BD%E5%AE%9E%E5%87%BD%E7%9A%84%E5%9B%9E%E5%A4%8D.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-062 | Manufacturer | 02-M02 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/02-M02.md | https://www.sinopep.com/cdmo-services/capacity/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-063 | Manufacturer | 02-M02 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/02-M02.md | https://www.sinopep.com/frequently-asked-questions/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-064 | Manufacturer | 02-M02 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/02-M02.md | https://www.pmda.go.jp/files/000240884.xlsx | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-065 | Manufacturer | 02-M02 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/02-M02.md | https://www.accessdata.fda.gov/cms_ia/importalert_189.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-066 | Manufacturer | 02-M02 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/02-M02.md | https://www.accessdata.fda.gov/cms_ia/importalert_1174.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-067 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://pdf.dfcfw.com/pdf/H2_AN202604291821715619_1.PDF?t=1782816592078 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-068 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://www.hybio.com/subsidiary/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-069 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://www.nmpa.gov.cn/directory/web/nmpa//xxgk/ggtg/ypggtg/ypgmprzh/ypgmprzhgg/ypgmpshj/20190115000001188.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-070 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://dailymed.nlm.nih.gov/dailymed/drugInfo.cfm?setid=2100ec49-57b2-4330-ab5f-057ce9b7e4d0 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-071 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://projects.propublica.org/rx-inspector/facilities/3011090684/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-072 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://pdf.dfcfw.com/pdf/H2_AN202111191529958067_1.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-073 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://www.gov.br/anvisa/pt-br/composicao/diretoria-colegiada/reunioes-da-diretoria/votos-dos-circuitos-deliberativos-1/2025/cd-0660-2025-voto.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-074 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://projects.propublica.org/rx-inspector/facilities/3016069760/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-075 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://www.nmpa.gov.cn/directory/web/nmpa/xxgk/ggtg/ypggtg/ypgmprzh/ypgmprzhgg/ypgmpshj/20181119000001285.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-076 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://cima.aemps.es/cima/publico/detalle.html?nregistro=84867 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-077 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://www.hybio.com/peptide-drug-development/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-078 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://www.hybio.com/crdmo-services/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-079 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://www.fda.gov/news-events/press-announcements/fda-approves-first-generic-once-daily-glp-1-injection-lower-blood-sugar-patients-type-2-diabetes | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-080 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://www.fda.gov/inspections-compliance-enforcement-and-criminal-investigations/inspection-basics/inspection-classifications | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-081 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://www.nmpa.gov.cn/directory/web/nmpa/zwfw/sdxx/sdxxyp/yppjfb/20230129155130147.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-082 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://www.nmpa.gov.cn/directory/web/nmpa/zwfw/sdxx/sdxxyp/yppjfb/20230202160812103.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-083 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://www.nmpa.gov.cn/zwfw/sdxx/sdxxyp/yppjfb/20260701155655187.html?type=pc&m= | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-084 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://www.hybio.com/zh/notice/announcement-on-the-wholly-owned-subsidiary-obtaining-the-austral/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-085 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | http://notice.10jqka.com.cn/api/pdf/e224e819098f4d2c_1744976591/%E7%BF%B0%E5%AE%87%E8%8D%AF%E4%B8%9A%EF%BC%9A%E5%85%B3%E4%BA%8E%E5%90%91%E9%9F%A9%E5%9B%BD%E9%A3%9F%E5%93%81%E8%8D%AF%E5%93%81%E5%AE%89%E5%85%A8%E5%A4%84%E6%8F%90%E4%BA%A4%E6%9B%BF%E5%B0%94%E6%B3%8A%E8%82%BD%E5%8E%9F%E6%96%99%E8%8D%AF%E7%99%BB%E8%AE%B0%E7%9A%84%E5%85%AC%E5%91%8A.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-086 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://www.hybio.com/news/hybio-pharmaceutical-s-longhua-headquarters-r-d-center-laboratory-passes-fda-inspection-again-with-zero-deficiencies/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-087 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://www.accessdata.fda.gov/CMS_IA/importalert_1186.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-088 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://disc.static.szse.cn/disc/disk03/finalpage/2023-08-14/0f7f53c8-77df-40f7-a9b9-6cc601875520.PDF | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-089 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | http://changchun.customs.gov.cn/shenzhen_customs/zfxxgk15/4956195/4956283/4962908/4972922/4972944/6586472/index.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-090 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://www.hybio.com/news/good-news-hybio-pharmaceutical-completes-official-nmpa-registration-for-tirzepatide-api/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-091 | Manufacturer | 03-M03 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/03-M03.md | https://www.hybio.com/news/good-news-hybio-pharmaceutical-completes-official-nmpa-registration-of-semaglutide-api/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-092 | Manufacturer | 04-M04 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/04-M04.md | https://www.kgi.com.hk/en/-/media/files/kgishk/pdf/ipoprospectus/hkipo_03880.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-093 | Manufacturer | 04-M04 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/04-M04.md | https://cpcscientific.com/medtide-inc-cpc-scientifics-parent-company-debuts-on-hong-kong-stock-exchange/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-094 | Manufacturer | 04-M04 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/04-M04.md | https://projects.propublica.org/rx-inspector/facilities/3004518843/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-095 | Manufacturer | 04-M04 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/04-M04.md | https://hbw.citeline.com/-/media/pmbi-old-site/supporting-documents/pharmasia-news/2012/june/warning-letter--chinese-peptide-co.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-096 | Manufacturer | 04-M04 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/04-M04.md | https://www.medtideinc.com/en/CompanyNews/info.aspx?itemid=327 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-097 | Manufacturer | 04-M04 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/04-M04.md | https://newsfile.moomoo.com/public/NN-PersistNoticeAttachment/7781/20260330/12078527-0.PDF | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-098 | Manufacturer | 04-M04 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/04-M04.md | https://cpcscientific.com/locations/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-099 | Manufacturer | 04-M04 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/04-M04.md | https://www.nmpa.gov.cn/directory/web/nmpa/xxgk/ggtg/ypggtg/ypgmprzh/ypgmprzhgg/ypgmpgjj/20100114165101245.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-100 | Manufacturer | 04-M04 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/04-M04.md | https://www.businesswire.com/news/home/20260805297284/en/CPC-Scientific-Announces-U.S.-FDA-Pre-License-Inspection-PLI-Successfully-Completed-at-Its-Hangzhou-cGMP-Manufacturing-Facility-for-Hepcludex-API-Establishing-a-Proven-Track-Record-Under-the-Stringent-BLA-Pathway | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-101 | Manufacturer | 04-M04 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/04-M04.md | https://static.propublica.org/fda-inspection-documents/483s/2024-10801%2F240010163_enc2_320.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-102 | Manufacturer | 04-M04 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/04-M04.md | https://cpcscientific.com/custom-peptide-synthesis/cgmp-peptide-manufacturing/capacity/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-103 | Manufacturer | 04-M04 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/04-M04.md | https://cpcscientific.com/custom-peptide-synthesis/cgmp-peptide-manufacturing/quality/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-104 | Manufacturer | 04-M04 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/04-M04.md | https://www.fda.gov/news-events/press-announcements/fda-approves-first-treatment-chronic-hepatitis-delta-virus-hdv-infection | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-105 | Manufacturer | 04-M04 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/04-M04.md | https://www.fda483s.com/fdadocs/chinese-peptide-company-hangzhou-china/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-106 | Manufacturer | 04-M04 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/04-M04.md | https://cpcscientific.com/cpc-scientifics-tirzepatide-api-successfully-secures-us-fda-dmf-filing/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-107 | Manufacturer | 04-M04 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/04-M04.md | https://cpcscientific.com/cpc-scientifics-gmp-manufacturing-facility-passes-german-inspection/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-108 | Manufacturer | 04-M04 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/04-M04.md | https://www.ema.europa.eu/en/medicines/human/EPAR/hepcludex | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-109 | Manufacturer | 04-M04 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/04-M04.md | https://www.medtideinc.com/en/companynews/info.aspx?itemid=328 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-110 | Manufacturer | 04-M04 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/04-M04.md | https://www.fda.gov/news-events/press-announcements/fda-launches-green-list-protect-americans-illegal-imported-glp-1-drug-ingredients | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-111 | Manufacturer | 05-M05 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/05-M05.md | https://extranet.who.int/prequal/medicines/active-pharmaceutical-ingredient/whoapi-361-oxytocin | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-112 | Manufacturer | 05-M05 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/05-M05.md | https://extranet.who.int/prequal/medicines/active-pharmaceutical-ingredient/whoapi-423-carbetocin | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-113 | Manufacturer | 05-M05 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/05-M05.md | https://extranet.who.int/prequal/medicines/rh083 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-114 | Manufacturer | 05-M05 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/05-M05.md | https://cdsco.gov.in/opencms/resources/UploadCDSCOWeb/2018/UploadInternationalCell/WC%20-0549%20-Piramal.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-115 | Manufacturer | 05-M05 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/05-M05.md | https://www.fda.gov/media/185578/download | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-116 | Manufacturer | 05-M05 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/05-M05.md | https://www.business-standard.com/markets/capital-market-news/piramal-pharma-gains-after-receiving-eir-for-turbhe-facility-from-usfda-125051200714_1.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-117 | Manufacturer | 05-M05 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/05-M05.md | https://www.health.gov.za/wp-content/uploads/2026/02/Current-Master-Health-Product-List-6-Feb-2026.xlsx | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-118 | Manufacturer | 05-M05 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/05-M05.md | https://www.piramalpharmasolutions.com/facilities/peptide-api-development-and-manufacturing-turbhe | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-119 | Manufacturer | 05-M05 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/05-M05.md | https://ppl-da-website-new-afd-endpoint-bgd4d0c9egf9g2eq.a01.azurefd.net/media/documents/Annual-Report-FY-2025-26.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-120 | Manufacturer | 05-M05 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/05-M05.md | https://www.piramalpharmasolutions.com/facilities/sterile-injectables-development-and-manufacturing-lexington | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-121 | Manufacturer | 05-M05 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/05-M05.md | https://www.business-standard.com/markets/capital-market-news/piramal-pharma-gets-eir-for-lexington-facility-from-us-fda-126041300272_1.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-122 | Manufacturer | 05-M05 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/05-M05.md | https://extranet.who.int/prequal/sites/default/files/whopar_files/RH083part6v2_1.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-123 | Manufacturer | 05-M05 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/05-M05.md | https://www.piramalpharmasolutions.com/resources/blogs/cost-effective-synthesis-of-complex-cyclic-peptides | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-124 | Manufacturer | 05-M05 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/05-M05.md | https://www.prnewswire.com/news-releases/piramal-pharma-solutions-expands-peptide-api-facility-with-advanced-spray-drying-suite-302842218.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-125 | Manufacturer | 05-M05 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/05-M05.md | https://www.prnewswire.com/news-releases/piramal-pharmas-fy2026-annual-report-showcases-global-scale-innovation-led-growth-and-sustainability-milestones-302819498.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-126 | Manufacturer | 05-M05 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/05-M05.md | https://www.pharmamanufacturing.com/industry-news/news/55271230/fda-hits-piramal-pharmas-api-plant-in-india-with-form-483-for-deficiencies | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-127 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://vbshilpa.com/pdf/Annual-report-results-2025-2026.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-128 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://vbshilpa.com/annual-reports.php | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-129 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://www.vbshilpa.com/locations.php | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-130 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://www.vbshilpa.com/pdf/Shilpa%20Pharma%20Lifesciences%20Limited,%20Received%20CEP%20from%20EDQM%20for%20API,%20Desmopressin.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-131 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://www.vbshilpa.com/pdf/Shilpa%20Pharma%20Lifesciences%20Limited,%20Received%20CEP%20from%20EDQM%20for%20API,%20Octreotide.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-132 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://www.vbshilpa.com/pdf/Shilpa%20Pharma%20Lifesciences%20Limited,%20Unit-1,%20Received%20EIR%20from%20USFDA.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-133 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://www.vbshilpa.com/pdf/Shilpa%20Pharma%20Lifesciences%20Ltd,%20Unit%20II,%20Raichur,%20Karnataka%20has%20cleared%20PMDA%20Japan,%20GMP%20inspection.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-134 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://www.vbshilpa.com/pdf/Shilpa%20Pharma%20Lifesciences%20Limited,%20Unit%202,%20Raichur,%20Karnataka%20has%20cleared%20the%20ANVISA-Brazil%20GMP%20inspection.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-135 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://www.vbshilpa.com/pdf/Europe%20GMP%20Approval%20of%20Shilpa%20Medicare%20Ltd.%20Unit%204,%20Jadcherla,%20Telangana..pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-136 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://www.fda.gov/inspections-compliance-enforcement-and-criminal-investigations/warning-letters/shilpa-medicare-limited-607877-10092020 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-137 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://shilpapharma.com/capabilities/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-138 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://shilpapharma.com/peptide-manufacturers/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-139 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://vbshilpa.com/peptides-gmp.php | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-140 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://www.biopharminternational.com/view/shilpa-medicare-launches-hybrid-cdmo-dcat-week-2025 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-141 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://vbshilpa.com/peptides-non-gmp-services.php | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-142 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://shilpapharma.com/analytical-services/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-143 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://www.edqm.eu/en/databases | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-144 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://www.sahpra.org.za/registered-health-products/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-145 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://www.vbshilpa.com/press-releases.php | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-146 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://www.vbshilpa.com/peptides-generic.php | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-147 | Manufacturer | 06-M06 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/06-M06.md | https://www.accessdata.fda.gov/drugsatfda_docs/nda/2024/215179Orig1s000OtherActionLtrs.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-148 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/company/outline/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-149 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://info.gbiz.go.jp/hojin/ichiran?hojinBango=5120901038915 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-150 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://www.peptidream.com/en/company/history/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-151 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://contents.xj-storage.jp/xcontents/45870/0f4e7954/5cfb/4ea6/97e3/9737ca27ce47/140120260216562906.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-152 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/en/news/20241111-2/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-153 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/en/news/20250326-2/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-154 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/en/news/20250417-2/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-155 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/en/service/peptide/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-156 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/en/technology/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-157 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/en/facility/manufacturing1/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-158 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/en/facility/manufacturing2/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-159 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/en/service/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-160 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://www.fda.gov/drugs/pharmaceutical-quality-resources/inspection-enforcement-resources | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-161 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://www.ema.europa.eu/en/human-regulatory-overview/research-development/compliance-research-development/good-manufacturing-practice/eudragmdp-database | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-162 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/en/facility/headquarters/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-163 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/en/facility/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-164 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://www.sumitomo-chem.co.jp/english/news/detail/20241111e.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-165 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/en/service/analysis/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-166 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/en/service/cmc/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-167 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/en/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-168 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/en/technology/microwave/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-169 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/en/technology/stagps/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-170 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/en/technology/syncsol/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-171 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/en/technology/hilic/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-172 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/en/technology/mcsgp/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-173 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/en/technology/lyophilization/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-174 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://www.asahi-kasei.com/news/2026/e260625 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-175 | Manufacturer | 07-M07 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/07-M07.md | https://peptistar.com/en/quality/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-176 | Manufacturer | 08-M08 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/08-M08.md | https://www.ajibio-pharma.com/news-post/ajinomoto-althea-and-omnichem-combine-to-form-ajinomoto-bio-pharma-services-reflecting-a-collective-range-of-services-offered-to-the-bio-pharma-industry/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-177 | Manufacturer | 08-M08 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/08-M08.md | https://www.ajioligos.com/en/about/specialists-in-oligonucleotides/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-178 | Manufacturer | 08-M08 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/08-M08.md | https://www.ajinomoto.com/aboutus/global_network | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-179 | Manufacturer | 08-M08 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/08-M08.md | https://www.ajibio-pharma.com/contact-us/japan/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-180 | Manufacturer | 08-M08 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/08-M08.md | https://www.ajibio-pharma.com/cdmo-services/oligo-peptide-synthesis/ajiphase-synthesis/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-181 | Manufacturer | 08-M08 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/08-M08.md | https://www.ajibio-pharma.com/cdmo-services/oligo-peptide-synthesis/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-182 | Manufacturer | 08-M08 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/08-M08.md | https://www.ajibio-pharma.com/cdmo-services/oligo-peptide-synthesis/solid-phase-synthesis/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-183 | Manufacturer | 08-M08 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/08-M08.md | https://www.ajibio-pharma.com/news-post/genedesign-joins-ajinomoto-bio-pharma-services-and-opens-oligonucleotide-api-development-center/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-184 | Manufacturer | 08-M08 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/08-M08.md | https://www.ajibio-pharma.com/news-post/first-commercial-drug-manufactured-via-ajinomoto-bio-pharma-services-ajiphase-technology-receives-fda-approval/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-185 | Manufacturer | 08-M08 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/08-M08.md | https://www.fda.gov/drugs/cder-foia-electronic-reading-room/ajinomoto-company-inc-02212025 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-186 | Manufacturer | 08-M08 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/08-M08.md | https://projects.propublica.org/rx-inspector/facilities/3002806336/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-187 | Manufacturer | 08-M08 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/08-M08.md | https://www.ajibio-pharma.com/news-post/ajinomoto-co-inc-to-sell-its-entire-equity-stake-in-ajinomoto-althea-a-us-based-aseptic-fill-finish-cdmo/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-188 | Manufacturer | 08-M08 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/08-M08.md | https://www.ajinomoto.co.jp/company/en/presscenter/press/detail/g2016_12_09.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-189 | Manufacturer | 08-M08 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/08-M08.md | https://www.ajibio-pharma.com/news-post/ajinomoto-bio-pharma-services-and-olon-s-p-a-form-strategic-partnership-to-advance-large-scale-peptide-and-protein-manufacturing/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-190 | Manufacturer | 08-M08 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/08-M08.md | https://ajibio-pharma.ajinomoto.com/corynex/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-191 | Manufacturer | 08-M08 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/08-M08.md | https://www.fda.gov/about-fda/fda-commissioner/ajinomoto-althea-inc-dba-ajinomoto-bio-pharma-services-san-diego-ca-483-issued-01162023 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-192 | Manufacturer | 08-M08 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/08-M08.md | https://www.ajibio-pharma.com/dedication-to-quality/quality-management/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-193 | Manufacturer | 08-M08 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/08-M08.md | https://www.ajibio-pharma.com/dedication-to-quality/regulatory-excellence/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-194 | Manufacturer | 08-M08 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/08-M08.md | https://www.ajibio-pharma.com/cdmo-services/oligo-peptide-synthesis/product-quality-analytical-testing/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-195 | Manufacturer | 08-M08 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/08-M08.md | https://www.ajibio-pharma.com/cdmo-services/oligo-peptide-synthesis/process-development/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-196 | Manufacturer | 09-M09 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/09-M09.md | https://kind.krx.co.kr/external/2026/05/15/002059/20260515004562/11013.htm | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-197 | Manufacturer | 09-M09 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/09-M09.md | https://www.fda.gov/drugs/drug-master-files-dmfs/list-drug-master-files-dmfs | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-198 | Manufacturer | 09-M09 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/09-M09.md | https://www.fda.gov/media/192069/download?attachment | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-199 | Manufacturer | 09-M09 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/09-M09.md | https://hlbpep.co.kr/kor/customer/notice.php?m=v&idx=1606 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-200 | Manufacturer | 09-M09 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/09-M09.md | https://hlbpep.co.kr/kor/customer/notice.php?m=v&idx=1548&pNo=1&code=notice | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-201 | Manufacturer | 09-M09 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/09-M09.md | http://hlbpep.co.kr/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-202 | Manufacturer | 09-M09 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/09-M09.md | https://kind.krx.co.kr/external/2026/07/10/000747/20260710001647/00636.htm | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-203 | Manufacturer | 09-M09 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/09-M09.md | https://www.accessdata.fda.gov/scripts/sda/sdDetailNavigation.cfm?sd=srolist&id=587C873A8BC53E9EE06346F0E10A144F&rownum=1160 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-204 | Manufacturer | 09-M09 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/09-M09.md | https://hlbpep.co.kr/kor/company/location.php | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-205 | Manufacturer | 09-M09 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/09-M09.md | https://hlbpep.co.kr/kor/customer/notice.php?m=v&idx=1398&pNo=2&code=notice | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-206 | Manufacturer | 09-M09 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/09-M09.md | https://kind.krx.co.kr/external/2024/03/20/000736/20240320003693/11011.htm | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-207 | Manufacturer | 09-M09 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/09-M09.md | https://kind.krx.co.kr/external/2026/03/12/001283/20260312003157/00591.htm | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-208 | Manufacturer | 09-M09 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/09-M09.md | https://hlbpep.co.kr/eng/peptides/generic.php | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-209 | Manufacturer | 09-M09 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/09-M09.md | http://hlbpep.co.kr/kor/company/history.php | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-210 | Manufacturer | 09-M09 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/09-M09.md | https://www.mfds.go.kr/eng/brd/m_19/view.do?seq=70331&srchFr=&srchTo=&srchWord=&srchTp=&itm_seq_1=0&itm_seq_2=0&multi_itm_seq=0&company_cd=&company_nm=&page=4 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-211 | Manufacturer | 09-M09 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/09-M09.md | https://kind.krx.co.kr/external/2025/04/14/000262/20250414000741/00636.htm | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-212 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.fda.gov.tw/TC/siteListContent.aspx?sid=2067&id=3723 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-213 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.fda.gov.tw/TC/siteListContent.aspx?sid=2067&id=39453 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-214 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://dailymed.nlm.nih.gov/dailymed/drugInfo.cfm?setid=707a64ef-964e-44a3-8a0f-fcc2eb5b1af2 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-215 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.accessdata.fda.gov/scripts/sda/sdDetailNavigation.cfm?sd=srolist&id=587C873A70A23E9EE06346F0E10A144F&rownum=1133 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-216 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.scinopharm.com/investor_document-detail/352/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-217 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.globalkeysolutions.net/records/fda_inspections/scinopharm-taiwan-ltd/ffdf6876-5ab7-4104-85ad-a0fd0f722d4f | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-218 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.fda.gov/media/184915/download | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-219 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.fda.gov/media/184916/download | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-220 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.scinopharm.com/news-detail/115/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-221 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://findbiz.nat.gov.tw/fts/company/16130161 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-222 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://findbiz.nat.gov.tw/fts/factory/08/94A00015 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-223 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.scinopharm.com/investor-detail/major-shareholders/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-224 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.scinopharm.com/brand/20/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-225 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.scinopharm.com/products-detail/56/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-226 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.scinopharm.com/products-detail/commercialAPI/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-227 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.scinopharm.com/news-detail/137/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-228 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.scinopharm.com/products-detail/54/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-229 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.scinopharm.com/news-detail/117/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-230 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.scinopharm.com/news-detail/139/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-231 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.scinopharm.com/download/57/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-232 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | http://jp.scinopharm.com/upload/download/files/220170913154210.PDF | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-233 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.scinopharm.com/about/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-234 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.globalkeysolutions.net/records/fda_inspections/scinopharm-taiwan-ltd/7044bf7c-e911-4e7c-84ce-056f5f8b6169 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-235 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.scinopharm.com/products-detail/60/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-236 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.scinopharm.com/solutions/QC/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-237 | Manufacturer | 10-M10 | /home/ubuntu/george_asia_peptide_due_diligence/manufacturers/10-M10.md | https://www.scinopharm.com/download/80/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-238 | Laboratory | 01-L01 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/01-L01.md | https://www.sgsgroup.com.cn/zh-cn/news/2025/01/sgs-shanghai-health-science-laboratory | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-239 | Laboratory | 01-L01 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/01-L01.md | https://www.sgsgroup.com.cn/-/media/sgscorp/documents/corporate/third-party-documents/1-cma20171021.cdn.en-CN.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-240 | Laboratory | 01-L01 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/01-L01.md | https://www.sgsgroup.com.cn/en-cn/our-company/about-sgs/sgs-in-china | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-241 | Laboratory | 01-L01 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/01-L01.md | https://www.prnasia.com/story/462074-1.shtml | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-242 | Laboratory | 01-L01 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/01-L01.md | https://www.sgsonline.com.cn/case/article/detail-7335.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-243 | Laboratory | 01-L01 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/01-L01.md | https://www.sgs.com/en/office-directory/sgs-china-shanghai-kangqiao-road-building-5-office | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-244 | Laboratory | 01-L01 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/01-L01.md | https://www.sgs.com/en-us/news/2023/03/announcing-the-grand-opening-of-sgss-new-bioanalytical-laboratory-in-shanghai-china | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-245 | Laboratory | 01-L01 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/01-L01.md | https://www.etics.org/eu_std_db/tl_scope_std.php?id_tl=124&id_products_category=6&s=1 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-246 | Laboratory | 01-L01 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/01-L01.md | https://las.cnas.org.cn/LAS_FQ/publish/suspendCancellationQuery.jsp?orgType=L | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-247 | Laboratory | 01-L01 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/01-L01.md | https://manufacturingchemist.com/sgs-expands-extractables-and-leachables-testing-capabilities-at-its-shanghai-facility--130532 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-248 | Laboratory | 01-L01 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/01-L01.md | https://www.sgsgroup.com.cn/en-cn/services/forced-degradation | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-249 | Laboratory | 01-L01 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/01-L01.md | https://www.fiercepharma.com/pharma-asia/sgs-life-science-services-completes-new-laboratories-at-its-shanghai-facility | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-250 | Laboratory | 01-L01 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/01-L01.md | https://www.sgsgroup.com.cn/en-cn/services/container-closure-integrity-testing | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-251 | Laboratory | 02-L02 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/02-L02.md | https://info.gbiz.go.jp/hojin/ichiran?hojinBango=9120001058249 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-252 | Laboratory | 02-L02 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/02-L02.md | https://www.pmda.go.jp/files/000277257.xlsx | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-253 | Laboratory | 02-L02 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/02-L02.md | https://www.pmda.go.jp/review-services/gmp-qms-gctp/gmp/0025.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-254 | Laboratory | 02-L02 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/02-L02.md | https://www.pmda.go.jp/english/about-pmda/0004.html | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-255 | Laboratory | 02-L02 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/02-L02.md | https://www.eurofins.com/ja-jp/biopharma-services/biopharma-product-testing/biopharmaceutical-characterization/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-256 | Laboratory | 02-L02 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/02-L02.md | https://cdnmedia.eurofins.com/apac/media/603045/001_company-profile_flyer.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-257 | Laboratory | 02-L02 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/02-L02.md | https://www.eurofins.com/ja-jp/biopharma-services/biopharma-product-testing/instrumentation/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-258 | Laboratory | 02-L02 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/02-L02.md | https://www.eurofins.com/ja-jp/biopharma-services/biopharma-product-testing/qc-testing/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-259 | Laboratory | 02-L02 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/02-L02.md | https://www.eurofins.com/ja-jp/biopharma-services/biopharma-product-testing/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-260 | Laboratory | 02-L02 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/02-L02.md | https://www.eurofins.com/ja-jp/biopharma-services/biopharma-product-testing/microbiological-testing/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-261 | Laboratory | 02-L02 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/02-L02.md | https://www.eurofins.com/ja-jp/biopharma-services/biopharma-product-testing/stability-testing/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-262 | Laboratory | 02-L02 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/02-L02.md | https://www.eurofins.com/ja-jp/biopharma-services/biopharma-product-testing/qc-testing/cci/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-263 | Laboratory | 02-L02 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/02-L02.md | https://www.eurofins.com/ja-jp/biopharma-services/biopharma-product-testing/impurity-testing/extractables-and-leachables/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-264 | Laboratory | 02-L02 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/02-L02.md | https://www.fda.gov/media/177453/download | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-265 | Laboratory | 02-L02 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/02-L02.md | https://www.eurofins.com/en/biopharma-services/news/eurofins-analytical-science-laboratories-expands-biologics/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-266 | Laboratory | 02-L02 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/02-L02.md | https://www.eurofins.com/ja-jp/biopharma-services/biopharma-product-testing/reference-standard-management/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-267 | Laboratory | 03-L03 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/03-L03.md | https://vimta.com/contact-us/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-268 | Laboratory | 03-L03 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/03-L03.md | https://extranet.who.int/prequal/quality-control-labs/india-vimta-genome-v | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-269 | Laboratory | 03-L03 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/03-L03.md | https://extranet.who.int/prequal/sites/default/files/whopir_files/WHOPIR_VimtaLabs_18-20January2023_0.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-270 | Laboratory | 03-L03 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/03-L03.md | https://extranet.who.int/prequal/medicines/prequalified/quality-control-labs | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-271 | Laboratory | 03-L03 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/03-L03.md | https://vimta.com/wp-content/uploads/2026/05/USFDA-EIR-communication_2023.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-272 | Laboratory | 03-L03 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/03-L03.md | https://vimta.com/wp-content/uploads/2026/05/EMA-Certificate.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-273 | Laboratory | 03-L03 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/03-L03.md | https://vimta.com/industries/drug-discovery-development/testing/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-274 | Laboratory | 03-L03 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/03-L03.md | https://vimta.com/industries/testing/mass-spec-analysis-peptides-proteins/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-275 | Laboratory | 03-L03 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/03-L03.md | https://vimta.com/extractables-leachables-studies/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-276 | Laboratory | 03-L03 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/03-L03.md | https://www.sahpra.org.za/wp-content/uploads/2022/06/SAHPGL-LIC-01-Guide-On-How-to-Apply-for-A-Licence-To-Manufacture_DN.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-277 | Laboratory | 03-L03 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/03-L03.md | https://nabl-india.org/nabl/index.php?c=publicaccredationdoc&m=index&docType=misc&per_page=75 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-278 | Laboratory | 03-L03 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/03-L03.md | https://vimta.com/industries/drug-discovery-development/cgmp-analytical-services/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-279 | Laboratory | 03-L03 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/03-L03.md | https://vimta.com/industries/cgmp-analytical-services/api-analysis/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-280 | Laboratory | 03-L03 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/03-L03.md | https://vimta.com/about-us/quality-management-system/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-281 | Laboratory | 03-L03 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/03-L03.md | https://extranet.who.int/prequal/news/new-who-public-inspection-reports-whopirs-published-90 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-282 | Laboratory | 04-L04 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/04-L04.md | https://cdn.intertek.com/www-intertek-com/media/countrysites/2026/Intertek-Pharmaceutical-Services-India-Brochure.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-283 | Laboratory | 04-L04 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/04-L04.md | https://cdn.intertek.com/www-intertek-com/dms-legacy/Intertek%20Terms%20%20Conditions%20of%20Business%20-%20INDIA.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-284 | Laboratory | 04-L04 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/04-L04.md | https://www.iasonline.org/ias_certificate/tl-1217/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-285 | Laboratory | 04-L04 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/04-L04.md | https://www.iasonline.org/wp-content/uploads/2023/12/TL-1217-Cert-New.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-286 | Laboratory | 04-L04 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/04-L04.md | https://bycsa.co/wp-content/uploads/2025/07/Acreditacion_de_laboratorio.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-287 | Laboratory | 04-L04 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/04-L04.md | https://dst.gov.in/sites/default/files/Certified%20Test%20Facilities%20withTest%20Items%20and%20Test%20Systems%2031072026.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-288 | Laboratory | 04-L04 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/04-L04.md | https://dst.gov.in/ngcma | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-289 | Laboratory | 04-L04 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/04-L04.md | https://www.intertek.com/india/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-290 | Laboratory | 04-L04 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/04-L04.md | https://www.intertek.com/contact/asiapacific/india/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-291 | Laboratory | 04-L04 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/04-L04.md | https://economictimes.indiatimes.com/company/intertek-india-private-limited/U74220DL1997PTC202243 | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-292 | Laboratory | 04-L04 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/04-L04.md | https://fda.maharashtra.gov.in/sections/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-293 | Laboratory | 04-L04 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/04-L04.md | https://www.linkedin.com/posts/intertek_biosciences-intertekindia-environmental-activity-7431793756342947840-sQbe | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-294 | Laboratory | 04-L04 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/04-L04.md | https://nabcb.qci.org.in/iaf-ilac-mla/iaf-intertek-india-pvt-ltd-mdqms033/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-295 | Laboratory | 04-L04 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/04-L04.md | https://nabl-india.org/nabl/uploads/List_of_Suspended_Labs_as_on_14-05-2026.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-296 | Laboratory | 04-L04 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/04-L04.md | https://nabl-india.org/nabl/uploads/List_of_Suspended_Labs_as_on_02-12-2025.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-297 | Laboratory | 04-L04 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/04-L04.md | https://www.intertek.com/pharmaceutical/biopharmaceuticals/peptide-analysis-and-formulation/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-298 | Laboratory | 04-L04 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/04-L04.md | https://www.intertek.com/pharmaceutical/analysis/qc/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-299 | Laboratory | 04-L04 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/04-L04.md | https://www.intertek.com/pharmaceutical/analysis/extractables-leachables/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-300 | Laboratory | 04-L04 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/04-L04.md | https://www.intertek.com/pharmaceutical/analysis/method-development-validation/ | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
SRC-301 | Laboratory | 04-L04 | /home/ubuntu/george_asia_peptide_due_diligence/laboratories/04-L04.md | https://www.sahpra.org.za/wp-content/uploads/2022/09/SAHPGL-INSP-04_v5Guidelines-for-Preparation-of-Site-Master-File.pdf | 20 August 2026 | See cited dossier/report; issuer claims require primary-record verification where identified.
Note on C9: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-001.
Note on D9: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-001.
Note on E9: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-001.
Note on F9: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-001.
Note on G9: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-001.
Note on H9: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-001.
Note on I9: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-001.
Note on C10: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-002.
Note on D10: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-002.
Note on E10: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-002.
Note on F10: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-002.
Note on G10: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-002.
Note on H10: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-002.
Note on I10: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-002.
Note on C11: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-003.
Note on D11: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-003.
Note on E11: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-003.
Note on F11: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-003.
Note on G11: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-003.
Note on H11: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-003.
Note on I11: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-003.
Note on C12: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-004.
Note on D12: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-004.
Note on E12: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-004.
Note on F12: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-004.
Note on G12: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-004.
Note on H12: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-004.
Note on I12: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-004.
Note on C13: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-005.
Note on D13: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-005.
Note on E13: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-005.
Note on F13: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-005.
Note on G13: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-005.
Note on H13: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-005.
Note on I13: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-005.
Note on C14: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-006.
Note on D14: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-006.
Note on E14: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-006.
Note on F14: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-006.
Note on G14: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-006.
Note on H14: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-006.
Note on I14: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-006.
Note on C15: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-007.
Note on D15: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-007.
Note on E15: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-007.
Note on F15: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-007.
Note on G15: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-007.
Note on H15: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-007.
Note on I15: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-007.
Note on C16: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-008.
Note on D16: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-008.
Note on E16: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-008.
Note on F16: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-008.
Note on G16: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-008.
Note on H16: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-008.
Note on I16: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-008.
Note on C17: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-009.
Note on D17: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-009.
Note on E17: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-009.
Note on F17: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-009.
Note on G17: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-009.
Note on H17: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-009.
Note on I17: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-009.
Note on C18: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-010.
Note on D18: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-010.
Note on E18: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-010.
Note on F18: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-010.
Note on G18: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-010.
Note on H18: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-010.
Note on I18: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-010.
Note on C19: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-011.
Note on D19: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-011.
Note on E19: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-011.
Note on F19: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-011.
Note on G19: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-011.
Note on H19: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-011.
Note on I19: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-011.
Note on C20: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-012.
Note on D20: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-012.
Note on E20: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-012.
Note on F20: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-012.
Note on G20: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-012.
Note on H20: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-012.
Note on I20: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-012.
Note on C21: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-013.
Note on D21: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-013.
Note on E21: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-013.
Note on F21: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-013.
Note on G21: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-013.
Note on H21: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-013.
Note on I21: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-013.
Note on C22: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-014.
Note on D22: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-014.
Note on E22: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-014.
Note on F22: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-014.
Note on G22: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-014.
Note on H22: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-014.
Note on I22: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-014.
Note on C23: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-015.
Note on D23: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-015.
Note on E23: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-015.
Note on F23: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-015.
Note on G23: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-015.
Note on H23: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-015.
Note on I23: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-015.
Note on C24: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-016.
Note on D24: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-016.
Note on E24: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-016.
Note on F24: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-016.
Note on G24: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-016.
Note on H24: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-016.
Note on I24: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-016.
Note on C25: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-017.
Note on D25: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-017.
Note on E25: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-017.
Note on F25: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-017.
Note on G25: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-017.
Note on H25: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-017.
Note on I25: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-017.
Note on C26: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-018.
Note on D26: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-018.
Note on E26: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-018.
Note on F26: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-018.
Note on G26: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-018.
Note on H26: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-018.
Note on I26: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-018.
Note on C27: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-019.
Note on D27: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-019.
Note on E27: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-019.
Note on F27: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-019.
Note on G27: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-019.
Note on H27: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-019.
Note on I27: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-019.
Note on C28: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-020.
Note on D28: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-020.
Note on E28: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-020.
Note on F28: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-020.
Note on G28: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-020.
Note on H28: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-020.
Note on I28: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-020.
Note on C29: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-021.
Note on D29: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-021.
Note on E29: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-021.
Note on F29: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-021.
Note on G29: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-021.
Note on H29: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-021.
Note on I29: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-021.
Note on C30: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-022.
Note on D30: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-022.
Note on E30: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-022.
Note on F30: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-022.
Note on G30: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-022.
Note on H30: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-022.
Note on I30: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-022.
Note on C31: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-023.
Note on D31: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-023.
Note on E31: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-023.
Note on F31: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-023.
Note on G31: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-023.
Note on H31: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-023.
Note on I31: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-023.
Note on C32: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-024.
Note on D32: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-024.
Note on E32: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-024.
Note on F32: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-024.
Note on G32: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-024.
Note on H32: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-024.
Note on I32: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-024.
Note on C33: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-025.
Note on D33: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-025.
Note on E33: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-025.
Note on F33: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-025.
Note on G33: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-025.
Note on H33: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-025.
Note on I33: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-025.
Note on C34: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-026.
Note on D34: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-026.
Note on E34: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-026.
Note on F34: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-026.
Note on G34: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-026.
Note on H34: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-026.
Note on I34: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-026.
Note on C35: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-027.
Note on D35: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-027.
Note on E35: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-027.
Note on F35: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-027.
Note on G35: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-027.
Note on H35: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-027.
Note on I35: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-027.
Note on C36: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-028.
Note on D36: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-028.
Note on E36: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-028.
Note on F36: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-028.
Note on G36: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-028.
Note on H36: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-028.
Note on I36: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-028.
Note on C37: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-029.
Note on D37: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-029.
Note on E37: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-029.
Note on F37: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-029.
Note on G37: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-029.
Note on H37: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-029.
Note on I37: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-029.
Note on C38: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-030.
Note on D38: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-030.
Note on E38: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-030.
Note on F38: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-030.
Note on G38: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-030.
Note on H38: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-030.
Note on I38: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-030.
Note on C39: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-031.
Note on D39: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-031.
Note on E39: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-031.
Note on F39: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-031.
Note on G39: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-031.
Note on H39: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-031.
Note on I39: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-031.
Note on C40: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-032.
Note on D40: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-032.
Note on E40: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-032.
Note on F40: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-032.
Note on G40: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-032.
Note on H40: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-032.
Note on I40: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-032.
Note on C41: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-033.
Note on D41: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-033.
Note on E41: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-033.
Note on F41: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-033.
Note on G41: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-033.
Note on H41: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-033.
Note on I41: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-033.
Note on C42: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-034.
Note on D42: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-034.
Note on E42: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-034.
Note on F42: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-034.
Note on G42: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-034.
Note on H42: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-034.
Note on I42: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-034.
Note on C43: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-035.
Note on D43: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-035.
Note on E43: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-035.
Note on F43: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-035.
Note on G43: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-035.
Note on H43: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-035.
Note on I43: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-035.
Note on C44: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-036.
Note on D44: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-036.
Note on E44: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-036.
Note on F44: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-036.
Note on G44: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-036.
Note on H44: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-036.
Note on I44: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-036.
Note on C45: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-037.
Note on D45: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-037.
Note on E45: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-037.
Note on F45: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-037.
Note on G45: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-037.
Note on H45: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-037.
Note on I45: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-037.
Note on C46: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-038.
Note on D46: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-038.
Note on E46: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-038.
Note on F46: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-038.
Note on G46: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-038.
Note on H46: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-038.
Note on I46: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-038.
Note on C47: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-039.
Note on D47: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-039.
Note on E47: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-039.
Note on F47: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-039.
Note on G47: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-039.
Note on H47: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-039.
Note on I47: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-039.
Note on C48: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-040.
Note on D48: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-040.
Note on E48: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-040.
Note on F48: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-040.
Note on G48: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-040.
Note on H48: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-040.
Note on I48: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-040.
Note on C49: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-041.
Note on D49: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-041.
Note on E49: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-041.
Note on F49: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-041.
Note on G49: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-041.
Note on H49: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-041.
Note on I49: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-041.
Note on C50: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-042.
Note on D50: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-042.
Note on E50: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-042.
Note on F50: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-042.
Note on G50: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-042.
Note on H50: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-042.
Note on I50: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-042.
Note on C51: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-043.
Note on D51: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-043.
Note on E51: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-043.
Note on F51: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-043.
Note on G51: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-043.
Note on H51: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-043.
Note on I51: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-043.
Note on C52: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-044.
Note on D52: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-044.
Note on E52: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-044.
Note on F52: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-044.
Note on G52: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-044.
Note on H52: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-044.
Note on I52: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-044.
Note on C53: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-045.
Note on D53: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-045.
Note on E53: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-045.
Note on F53: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-045.
Note on G53: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-045.
Note on H53: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-045.
Note on I53: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-045.
Note on C54: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-046.
Note on D54: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-046.
Note on E54: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-046.
Note on F54: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-046.
Note on G54: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-046.
Note on H54: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-046.
Note on I54: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-046.
Note on C55: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-047.
Note on D55: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-047.
Note on E55: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-047.
Note on F55: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-047.
Note on G55: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-047.
Note on H55: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-047.
Note on I55: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-047.
Note on C56: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-048.
Note on D56: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-048.
Note on E56: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-048.
Note on F56: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-048.
Note on G56: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-048.
Note on H56: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-048.
Note on I56: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-048.
Note on C57: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-049.
Note on D57: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-049.
Note on E57: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-049.
Note on F57: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-049.
Note on G57: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-049.
Note on H57: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-049.
Note on I57: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-049.
Note on C58: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-050.
Note on D58: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-050.
Note on E58: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-050.
Note on F58: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-050.
Note on G58: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-050.
Note on H58: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-050.
Note on I58: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-050.
Note on C59: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-051.
Note on D59: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-051.
Note on E59: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-051.
Note on F59: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-051.
Note on G59: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-051.
Note on H59: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-051.
Note on I59: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-051.
Note on C60: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-052.
Note on D60: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-052.
Note on E60: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-052.
Note on F60: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-052.
Note on G60: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-052.
Note on H60: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-052.
Note on I60: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-052.
Note on C61: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-053.
Note on D61: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-053.
Note on E61: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-053.
Note on F61: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-053.
Note on G61: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-053.
Note on H61: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-053.
Note on I61: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-053.
Note on C62: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-054.
Note on D62: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-054.
Note on E62: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-054.
Note on F62: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-054.
Note on G62: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-054.
Note on H62: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-054.
Note on I62: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-054.
Note on C63: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-055.
Note on D63: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-055.
Note on E63: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-055.
Note on F63: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-055.
Note on G63: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-055.
Note on H63: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-055.
Note on I63: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-055.
Note on C64: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-056.
Note on D64: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-056.
Note on E64: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-056.
Note on F64: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-056.
Note on G64: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-056.
Note on H64: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-056.
Note on I64: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-056.
Note on C65: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-057.
Note on D65: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-057.
Note on E65: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-057.
Note on F65: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-057.
Note on G65: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-057.
Note on H65: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-057.
Note on I65: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-057.
Note on C66: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-058.
Note on D66: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-058.
Note on E66: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-058.
Note on F66: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-058.
Note on G66: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-058.
Note on H66: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-058.
Note on I66: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-058.
Note on C67: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-059.
Note on D67: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-059.
Note on E67: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-059.
Note on F67: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-059.
Note on G67: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-059.
Note on H67: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-059.
Note on I67: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-059.
Note on C68: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-060.
Note on D68: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-060.
Note on E68: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-060.
Note on F68: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-060.
Note on G68: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-060.
Note on H68: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-060.
Note on I68: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-060.
Note on C69: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-061.
Note on D69: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-061.
Note on E69: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-061.
Note on F69: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-061.
Note on G69: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-061.
Note on H69: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-061.
Note on I69: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-061.
Note on C70: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-062.
Note on D70: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-062.
Note on E70: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-062.
Note on F70: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-062.
Note on G70: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-062.
Note on H70: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-062.
Note on I70: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-062.
Note on C71: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-063.
Note on D71: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-063.
Note on E71: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-063.
Note on F71: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-063.
Note on G71: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-063.
Note on H71: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-063.
Note on I71: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-063.
Note on C72: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-064.
Note on D72: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-064.
Note on E72: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-064.
Note on F72: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-064.
Note on G72: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-064.
Note on H72: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-064.
Note on I72: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-064.
Note on C73: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-065.
Note on D73: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-065.
Note on E73: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-065.
Note on F73: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-065.
Note on G73: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-065.
Note on H73: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-065.
Note on I73: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-065.
Note on C74: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-066.
Note on D74: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-066.
Note on E74: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-066.
Note on F74: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-066.
Note on G74: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-066.
Note on H74: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-066.
Note on I74: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-066.
Note on C75: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-067.
Note on D75: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-067.
Note on E75: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-067.
Note on F75: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-067.
Note on G75: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-067.
Note on H75: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-067.
Note on I75: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-067.
Note on C76: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-068.
Note on D76: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-068.
Note on E76: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-068.
Note on F76: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-068.
Note on G76: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-068.
Note on H76: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-068.
Note on I76: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-068.
Note on C77: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-069.
Note on D77: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-069.
Note on E77: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-069.
Note on F77: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-069.
Note on G77: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-069.
Note on H77: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-069.
Note on I77: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-069.
Note on C78: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-070.
Note on D78: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-070.
Note on E78: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-070.
Note on F78: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-070.
Note on G78: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-070.
Note on H78: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-070.
Note on I78: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-070.
Note on C79: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-071.
Note on D79: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-071.
Note on E79: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-071.
Note on F79: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-071.
Note on G79: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-071.
Note on H79: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-071.
Note on I79: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-071.
Note on C80: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-072.
Note on D80: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-072.
Note on E80: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-072.
Note on F80: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-072.
Note on G80: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-072.
Note on H80: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-072.
Note on I80: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-072.
Note on C81: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-073.
Note on D81: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-073.
Note on E81: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-073.
Note on F81: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-073.
Note on G81: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-073.
Note on H81: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-073.
Note on I81: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-073.
Note on C82: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-074.
Note on D82: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-074.
Note on E82: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-074.
Note on F82: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-074.
Note on G82: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-074.
Note on H82: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-074.
Note on I82: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-074.
Note on C83: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-075.
Note on D83: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-075.
Note on E83: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-075.
Note on F83: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-075.
Note on G83: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-075.
Note on H83: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-075.
Note on I83: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-075.
Note on C84: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-076.
Note on D84: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-076.
Note on E84: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-076.
Note on F84: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-076.
Note on G84: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-076.
Note on H84: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-076.
Note on I84: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-076.
Note on C85: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-077.
Note on D85: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-077.
Note on E85: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-077.
Note on F85: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-077.
Note on G85: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-077.
Note on H85: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-077.
Note on I85: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-077.
Note on C86: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-078.
Note on D86: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-078.
Note on E86: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-078.
Note on F86: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-078.
Note on G86: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-078.
Note on H86: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-078.
Note on I86: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-078.
Note on C87: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-079.
Note on D87: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-079.
Note on E87: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-079.
Note on F87: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-079.
Note on G87: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-079.
Note on H87: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-079.
Note on I87: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-079.
Note on C88: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-080.
Note on D88: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-080.
Note on E88: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-080.
Note on F88: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-080.
Note on G88: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-080.
Note on H88: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-080.
Note on I88: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-080.
Note on C89: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-081.
Note on D89: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-081.
Note on E89: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-081.
Note on F89: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-081.
Note on G89: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-081.
Note on H89: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-081.
Note on I89: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-081.
Note on C90: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-082.
Note on D90: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-082.
Note on E90: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-082.
Note on F90: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-082.
Note on G90: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-082.
Note on H90: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-082.
Note on I90: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-082.
Note on C91: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-083.
Note on D91: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-083.
Note on E91: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-083.
Note on F91: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-083.
Note on G91: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-083.
Note on H91: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-083.
Note on I91: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-083.
Note on C92: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-084.
Note on D92: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-084.
Note on E92: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-084.
Note on F92: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-084.
Note on G92: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-084.
Note on H92: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-084.
Note on I92: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-084.
Note on C93: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-085.
Note on D93: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-085.
Note on E93: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-085.
Note on F93: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-085.
Note on G93: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-085.
Note on H93: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-085.
Note on I93: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-085.
Note on C94: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-086.
Note on D94: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-086.
Note on E94: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-086.
Note on F94: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-086.
Note on G94: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-086.
Note on H94: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-086.
Note on I94: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-086.
Note on C95: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-087.
Note on D95: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-087.
Note on E95: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-087.
Note on F95: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-087.
Note on G95: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-087.
Note on H95: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-087.
Note on I95: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-087.
Note on C96: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-088.
Note on D96: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-088.
Note on E96: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-088.
Note on F96: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-088.
Note on G96: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-088.
Note on H96: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-088.
Note on I96: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-088.
Note on C97: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-089.
Note on D97: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-089.
Note on E97: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-089.
Note on F97: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-089.
Note on G97: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-089.
Note on H97: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-089.
Note on I97: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-089.
Note on C98: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-090.
Note on D98: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-090.
Note on E98: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-090.
Note on F98: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-090.
Note on G98: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-090.
Note on H98: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-090.
Note on I98: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-090.
Note on C99: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-091.
Note on D99: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-091.
Note on E99: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-091.
Note on F99: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-091.
Note on G99: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-091.
Note on H99: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-091.
Note on I99: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-091.
Note on C100: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-092.
Note on D100: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-092.
Note on E100: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-092.
Note on F100: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-092.
Note on G100: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-092.
Note on H100: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-092.
Note on I100: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-092.
Note on C101: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-093.
Note on D101: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-093.
Note on E101: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-093.
Note on F101: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-093.
Note on G101: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-093.
Note on H101: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-093.
Note on I101: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-093.
Note on C102: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-094.
Note on D102: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-094.
Note on E102: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-094.
Note on F102: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-094.
Note on G102: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-094.
Note on H102: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-094.
Note on I102: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-094.
Note on C103: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-095.
Note on D103: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-095.
Note on E103: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-095.
Note on F103: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-095.
Note on G103: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-095.
Note on H103: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-095.
Note on I103: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-095.
Note on C104: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-096.
Note on D104: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-096.
Note on E104: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-096.
Note on F104: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-096.
Note on G104: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-096.
Note on H104: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-096.
Note on I104: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-096.
Note on C105: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-097.
Note on D105: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-097.
Note on E105: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-097.
Note on F105: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-097.
Note on G105: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-097.
Note on H105: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-097.
Note on I105: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-097.
Note on C106: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-098.
Note on D106: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-098.
Note on E106: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-098.
Note on F106: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-098.
Note on G106: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-098.
Note on H106: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-098.
Note on I106: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-098.
Note on C107: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-099.
Note on D107: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-099.
Note on E107: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-099.
Note on F107: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-099.
Note on G107: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-099.
Note on H107: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-099.
Note on I107: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-099.
Note on C108: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-100.
Note on D108: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-100.
Note on E108: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-100.
Note on F108: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-100.
Note on G108: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-100.
Note on H108: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-100.
Note on I108: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-100.
Note on C109: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-101.
Note on D109: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-101.
Note on E109: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-101.
Note on F109: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-101.
Note on G109: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-101.
Note on H109: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-101.
Note on I109: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-101.
Note on C110: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-102.
Note on D110: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-102.
Note on E110: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-102.
Note on F110: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-102.
Note on G110: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-102.
Note on H110: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-102.
Note on I110: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-102.
Note on C111: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-103.
Note on D111: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-103.
Note on E111: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-103.
Note on F111: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-103.
Note on G111: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-103.
Note on H111: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-103.
Note on I111: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-103.
Note on C112: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-104.
Note on D112: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-104.
Note on E112: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-104.
Note on F112: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-104.
Note on G112: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-104.
Note on H112: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-104.
Note on I112: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-104.
Note on C113: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-105.
Note on D113: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-105.
Note on E113: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-105.
Note on F113: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-105.
Note on G113: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-105.
Note on H113: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-105.
Note on I113: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-105.
Note on C114: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-106.
Note on D114: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-106.
Note on E114: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-106.
Note on F114: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-106.
Note on G114: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-106.
Note on H114: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-106.
Note on I114: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-106.
Note on C115: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-107.
Note on D115: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-107.
Note on E115: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-107.
Note on F115: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-107.
Note on G115: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-107.
Note on H115: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-107.
Note on I115: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-107.
Note on C116: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-108.
Note on D116: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-108.
Note on E116: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-108.
Note on F116: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-108.
Note on G116: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-108.
Note on H116: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-108.
Note on I116: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-108.
Note on C117: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-109.
Note on D117: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-109.
Note on E117: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-109.
Note on F117: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-109.
Note on G117: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-109.
Note on H117: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-109.
Note on I117: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-109.
Note on C118: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-110.
Note on D118: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-110.
Note on E118: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-110.
Note on F118: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-110.
Note on G118: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-110.
Note on H118: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-110.
Note on I118: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-110.
Note on C119: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-111.
Note on D119: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-111.
Note on E119: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-111.
Note on F119: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-111.
Note on G119: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-111.
Note on H119: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-111.
Note on I119: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-111.
Note on C120: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-112.
Note on D120: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-112.
Note on E120: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-112.
Note on F120: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-112.
Note on G120: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-112.
Note on H120: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-112.
Note on I120: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-112.
Note on C121: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-113.
Note on D121: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-113.
Note on E121: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-113.
Note on F121: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-113.
Note on G121: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-113.
Note on H121: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-113.
Note on I121: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-113.
Note on C122: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-114.
Note on D122: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-114.
Note on E122: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-114.
Note on F122: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-114.
Note on G122: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-114.
Note on H122: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-114.
Note on I122: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-114.
Note on C123: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-115.
Note on D123: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-115.
Note on E123: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-115.
Note on F123: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-115.
Note on G123: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-115.
Note on H123: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-115.
Note on I123: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-115.
Note on C124: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-116.
Note on D124: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-116.
Note on E124: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-116.
Note on F124: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-116.
Note on G124: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-116.
Note on H124: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-116.
Note on I124: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-116.
Note on C125: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-117.
Note on D125: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-117.
Note on E125: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-117.
Note on F125: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-117.
Note on G125: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-117.
Note on H125: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-117.
Note on I125: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-117.
Note on C126: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-118.
Note on D126: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-118.
Note on E126: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-118.
Note on F126: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-118.
Note on G126: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-118.
Note on H126: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-118.
Note on I126: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-118.
Note on C127: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-119.
Note on D127: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-119.
Note on E127: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-119.
Note on F127: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-119.
Note on G127: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-119.
Note on H127: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-119.
Note on I127: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-119.
Note on C128: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-120.
Note on D128: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-120.
Note on E128: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-120.
Note on F128: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-120.
Note on G128: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-120.
Note on H128: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-120.
Note on I128: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-120.
Note on C129: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-121.
Note on D129: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-121.
Note on E129: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-121.
Note on F129: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-121.
Note on G129: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-121.
Note on H129: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-121.
Note on I129: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-121.
Note on C130: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-122.
Note on D130: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-122.
Note on E130: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-122.
Note on F130: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-122.
Note on G130: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-122.
Note on H130: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-122.
Note on I130: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-122.
Note on C131: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-123.
Note on D131: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-123.
Note on E131: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-123.
Note on F131: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-123.
Note on G131: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-123.
Note on H131: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-123.
Note on I131: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-123.
Note on C132: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-124.
Note on D132: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-124.
Note on E132: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-124.
Note on F132: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-124.
Note on G132: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-124.
Note on H132: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-124.
Note on I132: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-124.
Note on C133: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-125.
Note on D133: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-125.
Note on E133: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-125.
Note on F133: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-125.
Note on G133: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-125.
Note on H133: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-125.
Note on I133: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-125.
Note on C134: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-126.
Note on D134: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-126.
Note on E134: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-126.
Note on F134: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-126.
Note on G134: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-126.
Note on H134: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-126.
Note on I134: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-126.
Note on C135: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-127.
Note on D135: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-127.
Note on E135: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-127.
Note on F135: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-127.
Note on G135: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-127.
Note on H135: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-127.
Note on I135: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-127.
Note on C136: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-128.
Note on D136: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-128.
Note on E136: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-128.
Note on F136: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-128.
Note on G136: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-128.
Note on H136: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-128.
Note on I136: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-128.
Note on C137: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-129.
Note on D137: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-129.
Note on E137: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-129.
Note on F137: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-129.
Note on G137: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-129.
Note on H137: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-129.
Note on I137: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-129.
Note on C138: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-130.
Note on D138: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-130.
Note on E138: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-130.
Note on F138: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-130.
Note on G138: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-130.
Note on H138: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-130.
Note on I138: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-130.
Note on C139: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-131.
Note on D139: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-131.
Note on E139: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-131.
Note on F139: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-131.
Note on G139: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-131.
Note on H139: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-131.
Note on I139: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-131.
Note on C140: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-132.
Note on D140: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-132.
Note on E140: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-132.
Note on F140: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-132.
Note on G140: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-132.
Note on H140: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-132.
Note on I140: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-132.
Note on C141: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-133.
Note on D141: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-133.
Note on E141: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-133.
Note on F141: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-133.
Note on G141: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-133.
Note on H141: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-133.
Note on I141: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-133.
Note on C142: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-134.
Note on D142: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-134.
Note on E142: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-134.
Note on F142: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-134.
Note on G142: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-134.
Note on H142: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-134.
Note on I142: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-134.
Note on C143: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-135.
Note on D143: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-135.
Note on E143: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-135.
Note on F143: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-135.
Note on G143: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-135.
Note on H143: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-135.
Note on I143: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-135.
Note on C144: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-136.
Note on D144: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-136.
Note on E144: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-136.
Note on F144: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-136.
Note on G144: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-136.
Note on H144: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-136.
Note on I144: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-136.
Note on C145: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-137.
Note on D145: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-137.
Note on E145: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-137.
Note on F145: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-137.
Note on G145: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-137.
Note on H145: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-137.
Note on I145: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-137.
Note on C146: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-138.
Note on D146: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-138.
Note on E146: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-138.
Note on F146: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-138.
Note on G146: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-138.
Note on H146: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-138.
Note on I146: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-138.
Note on C147: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-139.
Note on D147: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-139.
Note on E147: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-139.
Note on F147: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-139.
Note on G147: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-139.
Note on H147: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-139.
Note on I147: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-139.
Note on C148: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-140.
Note on D148: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-140.
Note on E148: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-140.
Note on F148: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-140.
Note on G148: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-140.
Note on H148: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-140.
Note on I148: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-140.
Note on C149: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-141.
Note on D149: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-141.
Note on E149: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-141.
Note on F149: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-141.
Note on G149: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-141.
Note on H149: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-141.
Note on I149: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-141.
Note on C150: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-142.
Note on D150: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-142.
Note on E150: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-142.
Note on F150: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-142.
Note on G150: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-142.
Note on H150: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-142.
Note on I150: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-142.
Note on C151: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-143.
Note on D151: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-143.
Note on E151: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-143.
Note on F151: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-143.
Note on G151: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-143.
Note on H151: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-143.
Note on I151: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-143.
Note on C152: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-144.
Note on D152: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-144.
Note on E152: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-144.
Note on F152: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-144.
Note on G152: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-144.
Note on H152: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-144.
Note on I152: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-144.
Note on C153: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-145.
Note on D153: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-145.
Note on E153: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-145.
Note on F153: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-145.
Note on G153: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-145.
Note on H153: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-145.
Note on I153: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-145.
Note on C154: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-146.
Note on D154: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-146.
Note on E154: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-146.
Note on F154: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-146.
Note on G154: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-146.
Note on H154: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-146.
Note on I154: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-146.
Note on C155: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-147.
Note on D155: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-147.
Note on E155: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-147.
Note on F155: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-147.
Note on G155: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-147.
Note on H155: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-147.
Note on I155: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-147.
Note on C156: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-148.
Note on D156: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-148.
Note on E156: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-148.
Note on F156: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-148.
Note on G156: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-148.
Note on H156: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-148.
Note on I156: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-148.
Note on C157: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-149.
Note on D157: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-149.
Note on E157: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-149.
Note on F157: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-149.
Note on G157: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-149.
Note on H157: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-149.
Note on I157: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-149.
Note on C158: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-150.
Note on D158: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-150.
Note on E158: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-150.
Note on F158: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-150.
Note on G158: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-150.
Note on H158: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-150.
Note on I158: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-150.
Note on C159: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-151.
Note on D159: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-151.
Note on E159: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-151.
Note on F159: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-151.
Note on G159: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-151.
Note on H159: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-151.
Note on I159: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-151.
Note on C160: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-152.
Note on D160: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-152.
Note on E160: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-152.
Note on F160: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-152.
Note on G160: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-152.
Note on H160: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-152.
Note on I160: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-152.
Note on C161: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-153.
Note on D161: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-153.
Note on E161: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-153.
Note on F161: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-153.
Note on G161: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-153.
Note on H161: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-153.
Note on I161: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-153.
Note on C162: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-154.
Note on D162: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-154.
Note on E162: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-154.
Note on F162: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-154.
Note on G162: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-154.
Note on H162: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-154.
Note on I162: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-154.
Note on C163: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-155.
Note on D163: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-155.
Note on E163: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-155.
Note on F163: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-155.
Note on G163: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-155.
Note on H163: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-155.
Note on I163: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-155.
Note on C164: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-156.
Note on D164: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-156.
Note on E164: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-156.
Note on F164: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-156.
Note on G164: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-156.
Note on H164: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-156.
Note on I164: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-156.
Note on C165: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-157.
Note on D165: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-157.
Note on E165: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-157.
Note on F165: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-157.
Note on G165: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-157.
Note on H165: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-157.
Note on I165: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-157.
Note on C166: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-158.
Note on D166: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-158.
Note on E166: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-158.
Note on F166: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-158.
Note on G166: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-158.
Note on H166: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-158.
Note on I166: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-158.
Note on C167: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-159.
Note on D167: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-159.
Note on E167: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-159.
Note on F167: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-159.
Note on G167: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-159.
Note on H167: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-159.
Note on I167: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-159.
Note on C168: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-160.
Note on D168: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-160.
Note on E168: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-160.
Note on F168: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-160.
Note on G168: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-160.
Note on H168: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-160.
Note on I168: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-160.
Note on C169: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-161.
Note on D169: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-161.
Note on E169: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-161.
Note on F169: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-161.
Note on G169: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-161.
Note on H169: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-161.
Note on I169: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-161.
Note on C170: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-162.
Note on D170: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-162.
Note on E170: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-162.
Note on F170: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-162.
Note on G170: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-162.
Note on H170: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-162.
Note on I170: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-162.
Note on C171: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-163.
Note on D171: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-163.
Note on E171: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-163.
Note on F171: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-163.
Note on G171: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-163.
Note on H171: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-163.
Note on I171: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-163.
Note on C172: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-164.
Note on D172: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-164.
Note on E172: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-164.
Note on F172: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-164.
Note on G172: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-164.
Note on H172: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-164.
Note on I172: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-164.
Note on C173: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-165.
Note on D173: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-165.
Note on E173: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-165.
Note on F173: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-165.
Note on G173: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-165.
Note on H173: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-165.
Note on I173: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-165.
Note on C174: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-166.
Note on D174: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-166.
Note on E174: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-166.
Note on F174: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-166.
Note on G174: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-166.
Note on H174: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-166.
Note on I174: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-166.
Note on C175: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-167.
Note on D175: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-167.
Note on E175: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-167.
Note on F175: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-167.
Note on G175: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-167.
Note on H175: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-167.
Note on I175: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-167.
Note on C176: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-168.
Note on D176: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-168.
Note on E176: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-168.
Note on F176: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-168.
Note on G176: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-168.
Note on H176: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-168.
Note on I176: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-168.
Note on C177: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-169.
Note on D177: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-169.
Note on E177: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-169.
Note on F177: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-169.
Note on G177: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-169.
Note on H177: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-169.
Note on I177: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-169.
Note on C178: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-170.
Note on D178: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-170.
Note on E178: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-170.
Note on F178: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-170.
Note on G178: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-170.
Note on H178: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-170.
Note on I178: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-170.
Note on C179: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-171.
Note on D179: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-171.
Note on E179: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-171.
Note on F179: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-171.
Note on G179: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-171.
Note on H179: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-171.
Note on I179: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-171.
Note on C180: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-172.
Note on D180: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-172.
Note on E180: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-172.
Note on F180: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-172.
Note on G180: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-172.
Note on H180: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-172.
Note on I180: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-172.
Note on C181: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-173.
Note on D181: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-173.
Note on E181: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-173.
Note on F181: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-173.
Note on G181: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-173.
Note on H181: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-173.
Note on I181: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-173.
Note on C182: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-174.
Note on D182: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-174.
Note on E182: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-174.
Note on F182: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-174.
Note on G182: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-174.
Note on H182: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-174.
Note on I182: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-174.
Note on C183: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-175.
Note on D183: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-175.
Note on E183: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-175.
Note on F183: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-175.
Note on G183: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-175.
Note on H183: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-175.
Note on I183: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-175.
Note on C184: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-176.
Note on D184: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-176.
Note on E184: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-176.
Note on F184: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-176.
Note on G184: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-176.
Note on H184: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-176.
Note on I184: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-176.
Note on C185: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-177.
Note on D185: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-177.
Note on E185: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-177.
Note on F185: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-177.
Note on G185: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-177.
Note on H185: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-177.
Note on I185: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-177.
Note on C186: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-178.
Note on D186: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-178.
Note on E186: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-178.
Note on F186: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-178.
Note on G186: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-178.
Note on H186: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-178.
Note on I186: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-178.
Note on C187: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-179.
Note on D187: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-179.
Note on E187: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-179.
Note on F187: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-179.
Note on G187: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-179.
Note on H187: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-179.
Note on I187: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-179.
Note on C188: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-180.
Note on D188: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-180.
Note on E188: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-180.
Note on F188: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-180.
Note on G188: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-180.
Note on H188: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-180.
Note on I188: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-180.
Note on C189: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-181.
Note on D189: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-181.
Note on E189: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-181.
Note on F189: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-181.
Note on G189: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-181.
Note on H189: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-181.
Note on I189: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-181.
Note on C190: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-182.
Note on D190: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-182.
Note on E190: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-182.
Note on F190: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-182.
Note on G190: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-182.
Note on H190: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-182.
Note on I190: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-182.
Note on C191: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-183.
Note on D191: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-183.
Note on E191: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-183.
Note on F191: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-183.
Note on G191: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-183.
Note on H191: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-183.
Note on I191: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-183.
Note on C192: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-184.
Note on D192: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-184.
Note on E192: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-184.
Note on F192: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-184.
Note on G192: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-184.
Note on H192: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-184.
Note on I192: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-184.
Note on C193: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-185.
Note on D193: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-185.
Note on E193: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-185.
Note on F193: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-185.
Note on G193: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-185.
Note on H193: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-185.
Note on I193: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-185.
Note on C194: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-186.
Note on D194: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-186.
Note on E194: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-186.
Note on F194: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-186.
Note on G194: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-186.
Note on H194: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-186.
Note on I194: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-186.
Note on C195: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-187.
Note on D195: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-187.
Note on E195: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-187.
Note on F195: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-187.
Note on G195: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-187.
Note on H195: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-187.
Note on I195: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-187.
Note on C196: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-188.
Note on D196: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-188.
Note on E196: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-188.
Note on F196: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-188.
Note on G196: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-188.
Note on H196: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-188.
Note on I196: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-188.
Note on C197: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-189.
Note on D197: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-189.
Note on E197: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-189.
Note on F197: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-189.
Note on G197: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-189.
Note on H197: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-189.
Note on I197: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-189.
Note on C198: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-190.
Note on D198: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-190.
Note on E198: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-190.
Note on F198: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-190.
Note on G198: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-190.
Note on H198: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-190.
Note on I198: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-190.
Note on C199: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-191.
Note on D199: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-191.
Note on E199: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-191.
Note on F199: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-191.
Note on G199: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-191.
Note on H199: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-191.
Note on I199: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-191.
Note on C200: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-192.
Note on D200: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-192.
Note on E200: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-192.
Note on F200: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-192.
Note on G200: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-192.
Note on H200: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-192.
Note on I200: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-192.
Note on C201: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-193.
Note on D201: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-193.
Note on E201: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-193.
Note on F201: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-193.
Note on G201: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-193.
Note on H201: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-193.
Note on I201: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-193.
Note on C202: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-194.
Note on D202: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-194.
Note on E202: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-194.
Note on F202: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-194.
Note on G202: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-194.
Note on H202: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-194.
Note on I202: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-194.
Note on C203: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-195.
Note on D203: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-195.
Note on E203: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-195.
Note on F203: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-195.
Note on G203: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-195.
Note on H203: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-195.
Note on I203: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-195.
Note on C204: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-196.
Note on D204: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-196.
Note on E204: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-196.
Note on F204: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-196.
Note on G204: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-196.
Note on H204: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-196.
Note on I204: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-196.
Note on C205: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-197.
Note on D205: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-197.
Note on E205: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-197.
Note on F205: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-197.
Note on G205: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-197.
Note on H205: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-197.
Note on I205: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-197.
Note on C206: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-198.
Note on D206: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-198.
Note on E206: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-198.
Note on F206: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-198.
Note on G206: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-198.
Note on H206: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-198.
Note on I206: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-198.
Note on C207: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-199.
Note on D207: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-199.
Note on E207: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-199.
Note on F207: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-199.
Note on G207: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-199.
Note on H207: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-199.
Note on I207: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-199.
Note on C208: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-200.
Note on D208: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-200.
Note on E208: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-200.
Note on F208: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-200.
Note on G208: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-200.
Note on H208: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-200.
Note on I208: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-200.
Note on C209: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-201.
Note on D209: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-201.
Note on E209: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-201.
Note on F209: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-201.
Note on G209: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-201.
Note on H209: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-201.
Note on I209: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-201.
Note on C210: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-202.
Note on D210: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-202.
Note on E210: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-202.
Note on F210: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-202.
Note on G210: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-202.
Note on H210: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-202.
Note on I210: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-202.
Note on C211: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-203.
Note on D211: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-203.
Note on E211: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-203.
Note on F211: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-203.
Note on G211: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-203.
Note on H211: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-203.
Note on I211: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-203.
Note on C212: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-204.
Note on D212: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-204.
Note on E212: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-204.
Note on F212: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-204.
Note on G212: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-204.
Note on H212: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-204.
Note on I212: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-204.
Note on C213: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-205.
Note on D213: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-205.
Note on E213: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-205.
Note on F213: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-205.
Note on G213: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-205.
Note on H213: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-205.
Note on I213: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-205.
Note on C214: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-206.
Note on D214: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-206.
Note on E214: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-206.
Note on F214: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-206.
Note on G214: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-206.
Note on H214: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-206.
Note on I214: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-206.
Note on C215: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-207.
Note on D215: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-207.
Note on E215: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-207.
Note on F215: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-207.
Note on G215: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-207.
Note on H215: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-207.
Note on I215: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-207.
Note on C216: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-208.
Note on D216: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-208.
Note on E216: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-208.
Note on F216: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-208.
Note on G216: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-208.
Note on H216: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-208.
Note on I216: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-208.
Note on C217: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-209.
Note on D217: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-209.
Note on E217: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-209.
Note on F217: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-209.
Note on G217: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-209.
Note on H217: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-209.
Note on I217: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-209.
Note on C218: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-210.
Note on D218: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-210.
Note on E218: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-210.
Note on F218: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-210.
Note on G218: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-210.
Note on H218: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-210.
Note on I218: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-210.
Note on C219: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-211.
Note on D219: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-211.
Note on E219: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-211.
Note on F219: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-211.
Note on G219: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-211.
Note on H219: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-211.
Note on I219: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-211.
Note on C220: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-212.
Note on D220: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-212.
Note on E220: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-212.
Note on F220: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-212.
Note on G220: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-212.
Note on H220: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-212.
Note on I220: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-212.
Note on C221: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-213.
Note on D221: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-213.
Note on E221: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-213.
Note on F221: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-213.
Note on G221: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-213.
Note on H221: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-213.
Note on I221: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-213.
Note on C222: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-214.
Note on D222: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-214.
Note on E222: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-214.
Note on F222: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-214.
Note on G222: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-214.
Note on H222: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-214.
Note on I222: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-214.
Note on C223: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-215.
Note on D223: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-215.
Note on E223: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-215.
Note on F223: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-215.
Note on G223: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-215.
Note on H223: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-215.
Note on I223: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-215.
Note on C224: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-216.
Note on D224: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-216.
Note on E224: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-216.
Note on F224: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-216.
Note on G224: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-216.
Note on H224: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-216.
Note on I224: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-216.
Note on C225: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-217.
Note on D225: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-217.
Note on E225: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-217.
Note on F225: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-217.
Note on G225: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-217.
Note on H225: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-217.
Note on I225: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-217.
Note on C226: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-218.
Note on D226: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-218.
Note on E226: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-218.
Note on F226: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-218.
Note on G226: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-218.
Note on H226: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-218.
Note on I226: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-218.
Note on C227: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-219.
Note on D227: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-219.
Note on E227: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-219.
Note on F227: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-219.
Note on G227: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-219.
Note on H227: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-219.
Note on I227: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-219.
Note on C228: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-220.
Note on D228: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-220.
Note on E228: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-220.
Note on F228: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-220.
Note on G228: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-220.
Note on H228: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-220.
Note on I228: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-220.
Note on C229: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-221.
Note on D229: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-221.
Note on E229: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-221.
Note on F229: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-221.
Note on G229: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-221.
Note on H229: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-221.
Note on I229: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-221.
Note on C230: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-222.
Note on D230: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-222.
Note on E230: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-222.
Note on F230: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-222.
Note on G230: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-222.
Note on H230: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-222.
Note on I230: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-222.
Note on C231: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-223.
Note on D231: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-223.
Note on E231: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-223.
Note on F231: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-223.
Note on G231: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-223.
Note on H231: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-223.
Note on I231: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-223.
Note on C232: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-224.
Note on D232: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-224.
Note on E232: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-224.
Note on F232: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-224.
Note on G232: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-224.
Note on H232: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-224.
Note on I232: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-224.
Note on C233: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-225.
Note on D233: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-225.
Note on E233: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-225.
Note on F233: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-225.
Note on G233: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-225.
Note on H233: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-225.
Note on I233: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-225.
Note on C234: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-226.
Note on D234: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-226.
Note on E234: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-226.
Note on F234: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-226.
Note on G234: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-226.
Note on H234: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-226.
Note on I234: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-226.
Note on C235: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-227.
Note on D235: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-227.
Note on E235: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-227.
Note on F235: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-227.
Note on G235: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-227.
Note on H235: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-227.
Note on I235: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-227.
Note on C236: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-228.
Note on D236: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-228.
Note on E236: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-228.
Note on F236: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-228.
Note on G236: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-228.
Note on H236: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-228.
Note on I236: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-228.
Note on C237: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-229.
Note on D237: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-229.
Note on E237: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-229.
Note on F237: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-229.
Note on G237: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-229.
Note on H237: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-229.
Note on I237: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-229.
Note on C238: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-230.
Note on D238: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-230.
Note on E238: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-230.
Note on F238: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-230.
Note on G238: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-230.
Note on H238: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-230.
Note on I238: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-230.
Note on C239: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-231.
Note on D239: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-231.
Note on E239: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-231.
Note on F239: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-231.
Note on G239: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-231.
Note on H239: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-231.
Note on I239: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-231.
Note on C240: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-232.
Note on D240: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-232.
Note on E240: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-232.
Note on F240: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-232.
Note on G240: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-232.
Note on H240: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-232.
Note on I240: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-232.
Note on C241: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-233.
Note on D241: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-233.
Note on E241: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-233.
Note on F241: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-233.
Note on G241: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-233.
Note on H241: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-233.
Note on I241: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-233.
Note on C242: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-234.
Note on D242: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-234.
Note on E242: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-234.
Note on F242: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-234.
Note on G242: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-234.
Note on H242: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-234.
Note on I242: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-234.
Note on C243: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-235.
Note on D243: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-235.
Note on E243: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-235.
Note on F243: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-235.
Note on G243: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-235.
Note on H243: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-235.
Note on I243: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-235.
Note on C244: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-236.
Note on D244: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-236.
Note on E244: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-236.
Note on F244: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-236.
Note on G244: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-236.
Note on H244: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-236.
Note on I244: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-236.
Note on C245: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-237.
Note on D245: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-237.
Note on E245: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-237.
Note on F245: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-237.
Note on G245: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-237.
Note on H245: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-237.
Note on I245: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-237.
Note on C246: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-238.
Note on D246: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-238.
Note on E246: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-238.
Note on F246: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-238.
Note on G246: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-238.
Note on H246: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-238.
Note on I246: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-238.
Note on C247: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-239.
Note on D247: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-239.
Note on E247: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-239.
Note on F247: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-239.
Note on G247: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-239.
Note on H247: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-239.
Note on I247: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-239.
Note on C248: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-240.
Note on D248: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-240.
Note on E248: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-240.
Note on F248: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-240.
Note on G248: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-240.
Note on H248: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-240.
Note on I248: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-240.
Note on C249: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-241.
Note on D249: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-241.
Note on E249: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-241.
Note on F249: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-241.
Note on G249: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-241.
Note on H249: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-241.
Note on I249: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-241.
Note on C250: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-242.
Note on D250: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-242.
Note on E250: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-242.
Note on F250: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-242.
Note on G250: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-242.
Note on H250: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-242.
Note on I250: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-242.
Note on C251: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-243.
Note on D251: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-243.
Note on E251: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-243.
Note on F251: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-243.
Note on G251: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-243.
Note on H251: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-243.
Note on I251: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-243.
Note on C252: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-244.
Note on D252: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-244.
Note on E252: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-244.
Note on F252: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-244.
Note on G252: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-244.
Note on H252: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-244.
Note on I252: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-244.
Note on C253: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-245.
Note on D253: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-245.
Note on E253: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-245.
Note on F253: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-245.
Note on G253: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-245.
Note on H253: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-245.
Note on I253: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-245.
Note on C254: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-246.
Note on D254: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-246.
Note on E254: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-246.
Note on F254: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-246.
Note on G254: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-246.
Note on H254: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-246.
Note on I254: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-246.
Note on C255: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-247.
Note on D255: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-247.
Note on E255: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-247.
Note on F255: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-247.
Note on G255: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-247.
Note on H255: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-247.
Note on I255: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-247.
Note on C256: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-248.
Note on D256: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-248.
Note on E256: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-248.
Note on F256: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-248.
Note on G256: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-248.
Note on H256: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-248.
Note on I256: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-248.
Note on C257: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-249.
Note on D257: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-249.
Note on E257: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-249.
Note on F257: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-249.
Note on G257: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-249.
Note on H257: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-249.
Note on I257: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-249.
Note on C258: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-250.
Note on D258: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-250.
Note on E258: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-250.
Note on F258: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-250.
Note on G258: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-250.
Note on H258: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-250.
Note on I258: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-250.
Note on C259: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-251.
Note on D259: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-251.
Note on E259: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-251.
Note on F259: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-251.
Note on G259: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-251.
Note on H259: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-251.
Note on I259: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-251.
Note on C260: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-252.
Note on D260: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-252.
Note on E260: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-252.
Note on F260: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-252.
Note on G260: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-252.
Note on H260: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-252.
Note on I260: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-252.
Note on C261: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-253.
Note on D261: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-253.
Note on E261: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-253.
Note on F261: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-253.
Note on G261: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-253.
Note on H261: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-253.
Note on I261: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-253.
Note on C262: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-254.
Note on D262: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-254.
Note on E262: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-254.
Note on F262: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-254.
Note on G262: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-254.
Note on H262: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-254.
Note on I262: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-254.
Note on C263: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-255.
Note on D263: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-255.
Note on E263: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-255.
Note on F263: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-255.
Note on G263: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-255.
Note on H263: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-255.
Note on I263: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-255.
Note on C264: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-256.
Note on D264: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-256.
Note on E264: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-256.
Note on F264: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-256.
Note on G264: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-256.
Note on H264: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-256.
Note on I264: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-256.
Note on C265: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-257.
Note on D265: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-257.
Note on E265: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-257.
Note on F265: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-257.
Note on G265: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-257.
Note on H265: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-257.
Note on I265: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-257.
Note on C266: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-258.
Note on D266: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-258.
Note on E266: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-258.
Note on F266: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-258.
Note on G266: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-258.
Note on H266: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-258.
Note on I266: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-258.
Note on C267: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-259.
Note on D267: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-259.
Note on E267: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-259.
Note on F267: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-259.
Note on G267: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-259.
Note on H267: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-259.
Note on I267: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-259.
Note on C268: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-260.
Note on D268: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-260.
Note on E268: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-260.
Note on F268: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-260.
Note on G268: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-260.
Note on H268: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-260.
Note on I268: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-260.
Note on C269: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-261.
Note on D269: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-261.
Note on E269: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-261.
Note on F269: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-261.
Note on G269: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-261.
Note on H269: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-261.
Note on I269: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-261.
Note on C270: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-262.
Note on D270: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-262.
Note on E270: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-262.
Note on F270: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-262.
Note on G270: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-262.
Note on H270: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-262.
Note on I270: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-262.
Note on C271: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-263.
Note on D271: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-263.
Note on E271: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-263.
Note on F271: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-263.
Note on G271: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-263.
Note on H271: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-263.
Note on I271: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-263.
Note on C272: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-264.
Note on D272: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-264.
Note on E272: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-264.
Note on F272: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-264.
Note on G272: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-264.
Note on H272: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-264.
Note on I272: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-264.
Note on C273: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-265.
Note on D273: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-265.
Note on E273: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-265.
Note on F273: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-265.
Note on G273: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-265.
Note on H273: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-265.
Note on I273: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-265.
Note on C274: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-266.
Note on D274: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-266.
Note on E274: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-266.
Note on F274: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-266.
Note on G274: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-266.
Note on H274: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-266.
Note on I274: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-266.
Note on C275: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-267.
Note on D275: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-267.
Note on E275: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-267.
Note on F275: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-267.
Note on G275: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-267.
Note on H275: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-267.
Note on I275: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-267.
Note on C276: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-268.
Note on D276: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-268.
Note on E276: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-268.
Note on F276: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-268.
Note on G276: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-268.
Note on H276: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-268.
Note on I276: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-268.
Note on C277: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-269.
Note on D277: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-269.
Note on E277: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-269.
Note on F277: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-269.
Note on G277: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-269.
Note on H277: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-269.
Note on I277: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-269.
Note on C278: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-270.
Note on D278: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-270.
Note on E278: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-270.
Note on F278: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-270.
Note on G278: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-270.
Note on H278: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-270.
Note on I278: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-270.
Note on C279: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-271.
Note on D279: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-271.
Note on E279: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-271.
Note on F279: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-271.
Note on G279: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-271.
Note on H279: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-271.
Note on I279: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-271.
Note on C280: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-272.
Note on D280: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-272.
Note on E280: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-272.
Note on F280: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-272.
Note on G280: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-272.
Note on H280: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-272.
Note on I280: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-272.
Note on C281: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-273.
Note on D281: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-273.
Note on E281: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-273.
Note on F281: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-273.
Note on G281: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-273.
Note on H281: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-273.
Note on I281: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-273.
Note on C282: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-274.
Note on D282: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-274.
Note on E282: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-274.
Note on F282: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-274.
Note on G282: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-274.
Note on H282: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-274.
Note on I282: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-274.
Note on C283: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-275.
Note on D283: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-275.
Note on E283: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-275.
Note on F283: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-275.
Note on G283: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-275.
Note on H283: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-275.
Note on I283: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-275.
Note on C284: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-276.
Note on D284: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-276.
Note on E284: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-276.
Note on F284: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-276.
Note on G284: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-276.
Note on H284: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-276.
Note on I284: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-276.
Note on C285: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-277.
Note on D285: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-277.
Note on E285: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-277.
Note on F285: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-277.
Note on G285: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-277.
Note on H285: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-277.
Note on I285: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-277.
Note on C286: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-278.
Note on D286: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-278.
Note on E286: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-278.
Note on F286: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-278.
Note on G286: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-278.
Note on H286: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-278.
Note on I286: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-278.
Note on C287: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-279.
Note on D287: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-279.
Note on E287: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-279.
Note on F287: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-279.
Note on G287: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-279.
Note on H287: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-279.
Note on I287: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-279.
Note on C288: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-280.
Note on D288: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-280.
Note on E288: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-280.
Note on F288: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-280.
Note on G288: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-280.
Note on H288: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-280.
Note on I288: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-280.
Note on C289: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-281.
Note on D289: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-281.
Note on E289: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-281.
Note on F289: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-281.
Note on G289: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-281.
Note on H289: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-281.
Note on I289: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-281.
Note on C290: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-282.
Note on D290: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-282.
Note on E290: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-282.
Note on F290: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-282.
Note on G290: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-282.
Note on H290: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-282.
Note on I290: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-282.
Note on C291: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-283.
Note on D291: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-283.
Note on E291: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-283.
Note on F291: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-283.
Note on G291: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-283.
Note on H291: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-283.
Note on I291: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-283.
Note on C292: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-284.
Note on D292: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-284.
Note on E292: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-284.
Note on F292: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-284.
Note on G292: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-284.
Note on H292: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-284.
Note on I292: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-284.
Note on C293: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-285.
Note on D293: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-285.
Note on E293: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-285.
Note on F293: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-285.
Note on G293: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-285.
Note on H293: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-285.
Note on I293: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-285.
Note on C294: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-286.
Note on D294: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-286.
Note on E294: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-286.
Note on F294: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-286.
Note on G294: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-286.
Note on H294: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-286.
Note on I294: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-286.
Note on C295: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-287.
Note on D295: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-287.
Note on E295: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-287.
Note on F295: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-287.
Note on G295: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-287.
Note on H295: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-287.
Note on I295: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-287.
Note on C296: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-288.
Note on D296: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-288.
Note on E296: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-288.
Note on F296: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-288.
Note on G296: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-288.
Note on H296: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-288.
Note on I296: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-288.
Note on C297: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-289.
Note on D297: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-289.
Note on E297: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-289.
Note on F297: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-289.
Note on G297: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-289.
Note on H297: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-289.
Note on I297: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-289.
Note on C298: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-290.
Note on D298: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-290.
Note on E298: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-290.
Note on F298: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-290.
Note on G298: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-290.
Note on H298: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-290.
Note on I298: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-290.
Note on C299: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-291.
Note on D299: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-291.
Note on E299: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-291.
Note on F299: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-291.
Note on G299: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-291.
Note on H299: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-291.
Note on I299: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-291.
Note on C300: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-292.
Note on D300: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-292.
Note on E300: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-292.
Note on F300: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-292.
Note on G300: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-292.
Note on H300: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-292.
Note on I300: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-292.
Note on C301: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-293.
Note on D301: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-293.
Note on E301: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-293.
Note on F301: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-293.
Note on G301: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-293.
Note on H301: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-293.
Note on I301: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-293.
Note on C302: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-294.
Note on D302: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-294.
Note on E302: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-294.
Note on F302: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-294.
Note on G302: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-294.
Note on H302: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-294.
Note on I302: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-294.
Note on C303: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-295.
Note on D303: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-295.
Note on E303: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-295.
Note on F303: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-295.
Note on G303: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-295.
Note on H303: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-295.
Note on I303: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-295.
Note on C304: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-296.
Note on D304: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-296.
Note on E304: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-296.
Note on F304: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-296.
Note on G304: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-296.
Note on H304: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-296.
Note on I304: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-296.
Note on C305: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-297.
Note on D305: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-297.
Note on E305: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-297.
Note on F305: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-297.
Note on G305: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-297.
Note on H305: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-297.
Note on I305: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-297.
Note on C306: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-298.
Note on D306: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-298.
Note on E306: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-298.
Note on F306: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-298.
Note on G306: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-298.
Note on H306: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-298.
Note on I306: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-298.
Note on C307: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-299.
Note on D307: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-299.
Note on E307: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-299.
Note on F307: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-299.
Note on G307: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-299.
Note on H307: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-299.
Note on I307: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-299.
Note on C308: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-300.
Note on D308: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-300.
Note on E308: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-300.
Note on F308: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-300.
Note on G308: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-300.
Note on H308: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-300.
Note on I308: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-300.
Note on C309: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-301.
Note on D309: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-301.
Note on E309: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-301.
Note on F309: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-301.
Note on G309: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-301.
Note on H309: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-301.
Note on I309: Source: source_register.csv Decision date: 20 August 2026 Context: Source register row SRC-301.